PHOTON BROTHERS

Operations Suite

Complete User Guide

January 2026

# Overview

This suite of dashboards and reports provides end-to-end visibility and control over your solar installation pipeline, from initial sale through PTO (Permission to Operate). The tools are designed to work together, each serving a specific purpose in your operations workflow.

# Tool Categories

- STRATEGIC PLANNING - Leadership/Weekly Planning

- DAILY OPERATIONS - Operations Managers

- SCHEDULING & DISPATCH - Schedulers/Dispatchers

- FIELD OPERATIONS - Field Managers/Crews

- FINANCIAL TRACKING - Finance/PE Compliance

# 1. Strategic Planning Tools

## Dashboard Hub (pb-dashboard-hub.html)

Who uses it: Everyone

When to use: Starting point - navigate to any other dashboard

This is your central navigation portal. Open this first to access any other tool based on what you need to do.

## Pipeline Executive Summary (pipeline-executive-summary.html)

Who uses it: Leadership, Operations Directors

When to use: Weekly leadership meetings, board reviews, investor updates

### What it shows:

- Total pipeline value ($20.34M)

- Projects by stage (visual funnel)

- Location performance comparison

- Month-over-month trends

- Key risk indicators

## Revenue Forecast (revenue-forecast.xlsx)

Who uses it: Finance, Leadership, Sales

When to use: Monthly forecasting, cash flow planning, sales target setting

### Confidence Levels:

| Confidence | Meaning | Rate |
| --- | --- | --- |
| High | Install Complete or later | 80-95% |
| Medium | RTB through Construction | 50-79% |
| Low | Permitting stages | 25-49% |

# 2. Daily Operations Tools

## Unified Command Center (pb-unified-command-center.html)

Who uses it: Operations Managers, Regional Managers

When to use: Daily morning standup, throughout the day for monitoring

### How to use it:

- Morning routine: Open first thing to see overnight changes

- Check the Alert Panel: Red items need immediate attention

- PE Section: Green checkmarks = on track, Red X = at risk

- Filter by location to focus on your region

## Optimization Dashboard (pb-optimization-dashboard.html)

Who uses it: Operations Managers, Process Improvement

When to use: Identifying bottlenecks, process improvement initiatives

### Understanding Priority Scores:

The system calculates a score (0-1000+) based on:

- Days overdue (up to +100 per day overdue)

- PE status (+30-50 bonus for Participate Energy projects)

- Deal value (up to +30 for high-value deals)

Higher score = Schedule this project first

## AHJ/Utility Tracker (ahj-utility-tracker.xlsx)

Who uses it: Permitting Team, Operations Managers

When to use: Identifying slow jurisdictions, planning permit submissions

### How to use it:

- Before submitting permits: Check the AHJ score - low scores mean expect delays

- Escalation planning: Focus on jurisdictions with scores < 50

- Staffing decisions: High-volume slow AHJs may need dedicated resources

# 3. Scheduling & Dispatch Tools

## Master Scheduler v3 (pb-master-scheduler-v3.html)

Who uses it: Schedulers, Dispatch Coordinators

When to use: Building weekly/monthly schedules, reassigning jobs

### Weekly planning workflow:

- Review RTB projects in the left panel

- Check crew availability on the calendar

- Drag projects to available slots

- System warns if you exceed crew capacity

## Comprehensive Schedule (comprehensive-schedule.xlsx)

Who uses it: Operations Managers, Schedulers

When to use: Monthly planning, resource allocation

### 5 Sheets Explained:

| Sheet | Purpose |
| --- | --- |
| Summary | High-level view of schedulable projects |
| RTB Schedule | 26 projects ready to schedule NOW |
| Blocked-Action Req | 48 projects that need unblocking first |
| Pipeline-Coming Soon | 31 projects in permitting with estimated RTB dates |
| By Location | Breakdown per branch |

### Workflow:

- Start with RTB Schedule - these are your immediate priorities

- Review Blocked-Action Req - work to unblock these for next week

- Check Pipeline-Coming Soon - these will be RTB in 1-4 weeks

# 4. Field Operations Tools

## Mobile Dashboard (pb-mobile-dashboard.html)

Who uses it: Field Managers, Crew Leads (on phones/tablets)

When to use: On-site, in the field, quick reference

### Optimized for mobile devices with:

- Large touch targets

- Quick-glance status cards

- Swipe navigation

- One-tap to call customer or navigate to address

# 5. Financial & PE Tracking Tools

## Participate Energy Dashboard (participate-energy-dashboard.html)

Who uses it: PE Compliance Manager, Operations

When to use: Daily PE tracking, milestone management

CRITICAL FOR PE REVENUE!

### Milestone Overview:

| Milestone | Typical Deadline | Requirement |
| --- | --- | --- |
| M1 | Contract + 30 days | Site survey complete |
| M2 | M1 + 45 days | Permit submitted |
| M3 | M2 + 60 days | Install complete |
| M4 | M3 + 30 days | PTO received |

### How to use it:

- Daily: Check projects going RED (past deadline)

- Weekly: Review projects going YELLOW (within 14 days)

- Prioritize: PE projects should jump the queue when at risk

## PE Submission Export (pe-submission-export.xlsx)

Who uses it: PE Compliance Manager

When to use: Weekly PE portal updates

### Workflow:

- Download this file weekly

- Review for accuracy

- Upload to Participate Energy portal

- Track confirmation numbers

# Recommended Daily Workflows

## Operations Manager - Morning Routine (15 min)

- Open Unified Command Center - scan for red alerts

- Check Optimization Dashboard - review top 10 priority projects

- Open PE Dashboard - check for milestone risks

- Review any overnight updates in HubSpot

## Scheduler - Weekly Planning Session (1 hour)

- Open Comprehensive Schedule - RTB tab

- Cross-reference with Master Scheduler v3 - check crew availability

- Build next week's schedule using drag-drop

- Export and share with crews

## Leadership - Weekly Review (30 min)

- Pipeline Executive Summary - overall health

- Revenue Forecast - financial projections

- Weekly Operations Report - performance trends

- AHJ/Utility Tracker - any new problem jurisdictions?

# Quick Reference: Which Tool When?

| I need to... | Use this tool |
| --- | --- |
| See overall pipeline health | Pipeline Executive Summary |
| Find what to schedule next | Optimization Dashboard |
| Build next week's schedule | Master Scheduler v3 |
| Check PE milestone status | Participate Energy Dashboard |
| See my location's projects | Unified Command Center (filtered) |
| Forecast next quarter's revenue | Revenue Forecast |
| Identify slow permit jurisdictions | AHJ/Utility Tracker |
| Quick reference in the field | Mobile Dashboard |
| Upload data to PE portal | PE Submission Export |
| Review crew workload | Comprehensive Schedule |

# Current Pipeline Snapshot

| Metric | Value |
| --- | --- |
| Total Pipeline Value | $20.34M |
| Expected Revenue (6 months) | $6.84M |
| PE Revenue | $1.29M (18.9%) |
| RTB Ready | 26 projects |
| RTB Blocked | 48 projects |
| In Permitting | 31 projects |
| Inspection Backlog | 121 projects (BOTTLENECK) |

## Key Bottlenecks Identified

| Issue | Impact | Action |
| --- | --- | --- |
| Inspection Backlog | 121 projects, $4.77M | Add inspection resources |
| PE Milestone Risk | 38 projects, $1.52M | Prioritize PE in queue |
| San Luis Obispo | 95% overdue rate | Regional review needed |

# File Locations

All files are in the PB-Operations-Suite folder:

## dashboards/ (HTML - open in Chrome)

- pb-dashboard-hub.html - START HERE

- pb-unified-command-center.html

- pb-optimization-dashboard.html

- pb-master-scheduler-v3.html

- pb-mobile-dashboard.html

- participate-energy-dashboard.html

- pipeline-executive-summary.html

## reports/ (Excel)

- comprehensive-schedule.xlsx

- next-month-schedule.xlsx

- revenue-forecast.xlsx

- ahj-utility-tracker.xlsx

- pe-submission-export.xlsx

- weekly-operations-report.xlsx

## docs/

- PB-Operations-Suite-Guide.docx - This document

- PB-Quick-Reference-Card.docx - One-page summary

Photon Brothers Operations Suite - January 2026