## Summary
NEXT MONTH INSTALLATION SCHEDULE
Period: January 19 - February 16, 2026
CURRENT PIPELINE STATUS
Stage | Count | Value
Ready to Build (RTB) | 26 | 773905.22
RTB - Blocked | 48 | 2604270.69
Install Scheduled | 0 | 0
In Permitting (Coming Soon) | 31 | 1395921.28
Inspection Stage | 121 | 4766331.69
Install Complete | 0 | 0
PARTICIPATE ENERGY BREAKDOWN
Category | PE Count | % of Total
RTB Now | 16 | 62%
RTB Blocked | 22 | 46%
In Permitting | 6 | 19%
BY LOCATION
Location | RTB Now | Blocked | In Permitting | Weekly Capacity
Westminster | 4 | 13 | 9 | 15/week
Centennial | 1 | 15 | 12 | 10/week
Colorado Springs | 1 | 6 | 6 | 10/week
San Luis Obispo | 9 | 9 | 3 | 10/week
Camarillo | 10 | 5 | 1 | 10/week

## RTB Schedule
READY TO BUILD - INSTALLATION SCHEDULE
Projects currently in RTB stage - ready to install
Date | Location | Crew | Lead | Project | PE | Value | Days Overdue | Priority
2026-01-19 | San Luis Obispo | Team India | Ryan T. | PROJ-7370 | YES | 32950 | 333 | 489.59
2026-01-19 | Westminster | Team Charlie | Chris R. | PROJ-8006 | YES | 32006.72 | 161 | 317.4013
2026-01-20 | San Luis Obispo | Team India | Ryan T. | PROJ-7292 | YES | 21070 | 221 | 375.214
2026-01-20 | Westminster | Team Bravo | John D. | PROJ-8182 |  | 37387.86 | 127 | 234.4776
2026-01-20 | Westminster | Team Charlie | Chris R. | PROJ-8128 |  | 49459.9 | 117 | 226.892
2026-01-20 | Camarillo | Team Juliet | Mark H. | PROJ-8091 | YES | 63744.75 | 149 | 311.7489
2026-01-21 | Camarillo | Team Juliet | Mark H. | PROJ-8609 | YES | 29944.34 | 68 | 223.9889
2026-01-21 | Colorado Springs | Team Foxtrot | Tom K. | PROJ-8723 | YES | 33489.9 | 13 | 169.698
2026-01-22 | Camarillo | Team Juliet | Mark H. | PROJ-8683 | YES | 55767.89 | 49 | 210.1536
2026-01-22 | Camarillo | Team Kilo | Jeff C. | PROJ-8697 | YES | 18203.94 | 47 | 200.6408
2026-01-23 | San Luis Obispo | Team India | Ryan T. | PROJ-7945 |  | 28399.55 | 200 | 305.6799
2026-01-23 | Camarillo | Team Juliet | Mark H. | PROJ-8466 |  | 5600 | 89 | 190.12
2026-01-23 | Centennial | Team Echo | Steve L. | PROJ-8535 |  | 18291 | 61 | 164.6582
2026-01-26 | San Luis Obispo | Team Hotel | Alex P. | PROJ-7981 | YES | 12043.47 | 152 | 304.4087
2026-01-26 | Westminster | Team Alpha | Mike S. | PROJ-8771 |  | 34258 |  | 84.8516
2026-01-26 | Camarillo | Team Juliet | Mark H. | PROJ-8730 | YES | 42966 | 34 | 172.5932
2026-01-26 | Camarillo | Team Kilo | Jeff C. | PROJ-8749 | YES | 29431.08 | 27 | 162.8862
2026-01-27 | San Luis Obispo | Team India | Ryan T. | PROJ-8596 |  | 36274 | 92 | 199.2548
2026-01-27 | Camarillo | Team Juliet | Mark H. | PROJ-8810 | YES | 18203.94 | 1 | 134.6408
2026-01-27 | Camarillo | Team Kilo | Jeff C. | PROJ-8832 | YES | 13198.8 |  | 109.6398
2026-01-28 | San Luis Obispo | Team Hotel | Alex P. | PROJ-8762 | YES | 25971.4 | 44 | 199.1943
2026-01-28 | San Luis Obispo | Team India | Ryan T. | PROJ-8540 | YES | 42771.6 | 20 | 178.5543
2026-01-28 | Camarillo | Team Juliet | Mark H. | PROJ-8943 |  | 2750 |  | 0.55
2026-01-29 | San Luis Obispo | Team Hotel | Alex P. | PROJ-8632 | YES | 24219 | 28 | 162.8438
2026-01-29 | San Luis Obispo | Team India | Ryan T. | PROJ-8846 |  | 23800 | 5 | 109.76

## Blocked - Action Req
RTB-BLOCKED PROJECTS - REQUIRE UNBLOCKING
These projects are ready to build but blocked - need action to proceed
Project | Location | PE | Value | Days Overdue | Priority | Tentative Date | Crew
PROJ-7367 | San Luis Obispo | YES | 12334 | 348 | 500.4668 | 2026-01-19 | SLO-HOTEL
PROJ-7064 | Centennial |  | 39978 | 391 | 498.9956 | 2026-01-19 | CT-DELTA
PROJ-7353 | Westminster | YES | 30872.4 | 321 | 477.1745 | 2026-01-19 | WM-ALPHA
PROJ-7035 | Centennial |  | 887388.82 | 344 | 474 | 2026-01-19 | CT-ECHO
PROJ-7729 | San Luis Obispo | YES | 43621.6 | 272 | 430.7243 | 2026-01-20 | SLO-HOTEL
PROJ-7777 | Westminster | YES | 37194.8 | 223 | 380.439 | 2026-01-19 | WM-BRAVO
PROJ-7428 | Camarillo |  | 22250 | 275 | 379.45 | 2026-01-19 | CAM-JULIET
PROJ-7932 | San Luis Obispo | YES | 41702.08 | 216 | 374.3404 | 2026-01-21 | SLO-HOTEL
PROJ-8026 | San Luis Obispo | YES | 55000 | 183 | 344 | 2026-01-21 | SLO-INDIA
PROJ-7756 | Camarillo |  | 30325 | 236 | 342.065 | 2026-01-19 | CAM-KILO
PROJ-7760 | Centennial |  | 40000 | 215 | 323 | 2026-01-20 | CT-DELTA
PROJ-7963 | San Luis Obispo | YES | 38994.34 | 159 | 316.7989 | 2026-01-22 | SLO-HOTEL
PROJ-8162 | San Luis Obispo | YES | 37146.9 | 157 | 314.4294 | 2026-01-22 | SLO-INDIA
PROJ-8217 | San Luis Obispo | YES | 52018.72 | 147 | 307.4037 | 2026-01-23 | SLO-HOTEL
PROJ-8194 | Colorado Springs | YES | 33837.15 | 110 | 266.7674 | 2026-01-19 | CS-FOXTROT
PROJ-8048 | Westminster |  | 70000 | 152 | 266 | 2026-01-20 | WM-ALPHA
PROJ-8634 | San Luis Obispo | YES | 37679.56 | 81 | 238.5359 | 2026-01-26 | SLO-INDIA
PROJ-8320 | Camarillo |  | 10226.82 | 132 | 234.0454 | 2026-01-20 | CAM-KILO
PROJ-8618 | Centennial | YES | 33839.37 | 71 | 227.7679 | 2026-01-20 | CT-ECHO
PROJ-8381 | Colorado Springs | YES | 27402.53 | 69 | 224.4805 | 2026-01-19 | CS-GOLF
PROJ-8656 | Camarillo | YES | 62941.49 | 56 | 218.5883 | 2026-01-21 | CAM-KILO
PROJ-8650 | Centennial | YES | 56203.17 | 46 | 207.2406 | 2026-01-21 | CT-DELTA
PROJ-6351 | San Luis Obispo |  | 60000 | 95 | 207 | 2026-01-27 | SLO-HOTEL
PROJ-8295 | Centennial |  | 34455.12 | 99 | 205.891 | 2026-01-21 | CT-ECHO
PROJ-8642 | Westminster | YES | 63792.64 | 38 | 200.7585 | 2026-01-21 | WM-ALPHA
PROJ-8660 | Colorado Springs | YES | 30059.08 | 40 | 196.0118 | 2026-01-20 | CS-FOXTROT
PROJ-8415 | Centennial |  | 16102.22 | 91 | 194.2204 | 2026-01-22 | CT-DELTA
PROJ-8694 | Centennial | YES | 30825.06 | 37 | 193.165 | 2026-01-22 | CT-ECHO
PROJ-8677 | Centennial | YES | 41314.62 | 33 | 191.2629 | 2026-01-23 | CT-DELTA
PROJ-8472 | Camarillo | YES | 30478 | 34 | 190.0956 | 2026-01-23 | CAM-KILO
PROJ-8524 | Colorado Springs |  | 52251.61 | 71 | 181.4503 | 2026-01-20 | CS-GOLF
PROJ-8548 | Westminster |  | 46724.61 | 72 | 181.3449 | 2026-01-21 | WM-BRAVO
PROJ-8743 | Westminster | YES | 16743.65 | 21 | 174.3487 | 2026-01-21 | WM-CHARLIE
PROJ-8519 | Westminster |  | 33146.05 | 67 | 173.6292 | 2026-01-22 | WM-ALPHA
PROJ-8539 | Westminster |  | 38900.62 | 65 | 172.7801 | 2026-01-22 | WM-BRAVO
PROJ-8554 | Westminster |  | 50348.55 | 62 | 172.0697 | 2026-01-22 | WM-CHARLIE
PROJ-8521 | Westminster |  | 31625.34 | 59 | 165.3251 | 2026-01-23 | WM-ALPHA
PROJ-8702 | Westminster |  | 55292.12 | 51 | 162.0584 | 2026-01-23 | WM-BRAVO
PROJ-8636 | Westminster |  | 17680.04 | 46 | 149.536 | 2026-01-23 | WM-CHARLIE
PROJ-8528 | Centennial |  | 38479.73 | 36 | 143.6959 | 2026-01-26 | CT-DELTA
PROJ-8449 | Centennial |  | 33228 | 26 | 132.6456 | 2026-01-26 | CT-ECHO
PROJ-8724 | Centennial |  | 18291 | 28 | 131.6582 | 2026-01-27 | CT-DELTA
PROJ-8764 | Centennial |  | 14066.63 | 15 | 117.8133 | 2026-01-27 | CT-ECHO
PROJ-8783 | Westminster |  | 33845.24 |  | 81.769 | 2026-01-26 | WM-BRAVO
PROJ-8778 | Colorado Springs | YES | 26837.91 |  | 35.3676 | 2026-01-21 | CS-GOLF
PROJ-8794 | Colorado Springs |  | 39174.69 |  | 7.8349 | 2026-01-22 | CS-FOXTROT
PROJ-8409 | Centennial |  | 25851 |  | 5.1702 | 2026-01-28 | CT-DELTA
PROJ-8847 | Centennial |  | 23800.41 |  | 4.7601 | 2026-01-28 | CT-ECHO

## Pipeline - Coming Soon
IN PERMITTING - UPCOMING RTB PROJECTS
Projects currently in permitting that will become RTB soon
Project | Location | Current Stage | PE | Value | Est. Days to RTB | Est. RTB Date
PROJ-8836 | Colorado Springs | Permitting & Interconnection |  | 65596.58 | 0 | 2026-01-17
PROJ-8821 | Westminster | Permitting & Interconnection |  | 41147.14 | 0 | 2026-01-17
PROJ-8784 | Centennial | Permitting & Interconnection |  | 40168.36 | 0 | 2026-01-17
PROJ-8795 | Centennial | Permitting & Interconnection |  | 17791 | 0 | 2026-01-17
PROJ-8789 | Westminster | Permitting & Interconnection |  | 47070.03 | 0 | 2026-01-17
PROJ-8793 | Centennial | Permitting & Interconnection |  | 26175.82 | 0 | 2026-01-17
PROJ-8763 | Colorado Springs | Permitting & Interconnection |  | 8662.66 | 0 | 2026-01-17
PROJ-8740 | San Luis Obispo | Permitting & Interconnection | YES | 37403.08 | 0 | 2026-01-17
PROJ-8691 | Westminster | Permitting & Interconnection |  | 22855.04 | 0 | 2026-01-17
PROJ-8704 | Westminster | Permitting & Interconnection |  | 50129.69 | 0 | 2026-01-17
PROJ-8798 | Westminster | Permitting & Interconnection |  | 56663.04 | 0 | 2026-01-17
PROJ-8752 | San Luis Obispo | Permitting & Interconnection | YES | 39461.18 | 0 | 2026-01-17
PROJ-8686 | Colorado Springs | Permitting & Interconnection | YES | 42314.62 | 0 | 2026-01-17
PROJ-8680 | Colorado Springs | Permitting & Interconnection |  | 41534.59 | 0 | 2026-01-17
PROJ-8732 | Centennial | Permitting & Interconnection |  | 16689.01 | 0 | 2026-01-17
PROJ-8787 | Westminster | Permitting & Interconnection |  | 112312.2 | 0 | 2026-01-17
PROJ-8450 | Camarillo | Permitting & Interconnection | YES | 94561.91 | 0 | 2026-01-17
PROJ-8558 | Centennial | Permitting & Interconnection |  | 41104.86 | 0 | 2026-01-17
PROJ-8457 | San Luis Obispo | Permitting & Interconnection | YES | 49041.58 | 0 | 2026-01-17
PROJ-8480 | Westminster | Permitting & Interconnection |  | 57688.54 | 0 | 2026-01-17
PROJ-8368 | Centennial | Permitting & Interconnection |  | 44844 | 0 | 2026-01-17
PROJ-7825 | Colorado Springs | Permitting & Interconnection |  | 90400.4 | 0 | 2026-01-17
PROJ-8790 | Centennial | Permitting & Interconnection |  | 40887.81 | 0 | 2026-01-17
PROJ-8770 | Westminster | Permitting & Interconnection |  | 44315.88 | 0 | 2026-01-17
PROJ-8853 | Centennial | Permitting & Interconnection |  | 18291 | 8 | 2026-01-25
PROJ-8854 | Centennial | Permitting & Interconnection |  | 26796.24 | 8 | 2026-01-25
PROJ-8860 | Centennial | Permitting & Interconnection |  | 36809.66 | 16 | 2026-02-02
PROJ-8862 | Centennial | Permitting & Interconnection |  | 14314.54 | 16 | 2026-02-02
PROJ-8863 | Westminster | Permitting & Interconnection |  | 44535.14 | 17 | 2026-02-03
PROJ-8901 | Centennial | Permitting & Interconnection |  | 54252.88 | 35 | 2026-02-21
PROJ-8909 | Colorado Springs | Permitting & Interconnection | YES | 72102.8 | 41 | 2026-02-27

## Westminster
Westminster - COMPLETE SCHEDULE
Crews: Team Alpha (Mike S.), Team Bravo (John D.), Team Charlie (Chris R.)
Status: 4 RTB ¦ 13 Blocked ¦ 9 In Permitting
Date | Crew | Lead | Project | Stage | PE | Value | Notes
2026-01-19 | Team Alpha | Mike S. | PROJ-7353 | RTB - Blocked | YES | 30872.4 | BLOCKED - needs unblocking
2026-01-19 | Team Bravo | John D. | PROJ-7777 | RTB - Blocked | YES | 37194.8 | BLOCKED - needs unblocking
2026-01-19 | Team Charlie | Chris R. | PROJ-8006 | Ready To Build | YES | 32006.72
2026-01-20 | Team Alpha | Mike S. | PROJ-8048 | RTB - Blocked |  | 70000 | BLOCKED - needs unblocking
2026-01-20 | Team Bravo | John D. | PROJ-8182 | Ready To Build |  | 37387.86
2026-01-20 | Team Charlie | Chris R. | PROJ-8128 | Ready To Build |  | 49459.9
2026-01-21 | Team Alpha | Mike S. | PROJ-8642 | RTB - Blocked | YES | 63792.64 | BLOCKED - needs unblocking
2026-01-21 | Team Bravo | John D. | PROJ-8548 | RTB - Blocked |  | 46724.61 | BLOCKED - needs unblocking
2026-01-21 | Team Charlie | Chris R. | PROJ-8743 | RTB - Blocked | YES | 16743.65 | BLOCKED - needs unblocking
2026-01-22 | Team Alpha | Mike S. | PROJ-8519 | RTB - Blocked |  | 33146.05 | BLOCKED - needs unblocking
2026-01-22 | Team Bravo | John D. | PROJ-8539 | RTB - Blocked |  | 38900.62 | BLOCKED - needs unblocking
2026-01-22 | Team Charlie | Chris R. | PROJ-8554 | RTB - Blocked |  | 50348.55 | BLOCKED - needs unblocking
2026-01-23 | Team Alpha | Mike S. | PROJ-8521 | RTB - Blocked |  | 31625.34 | BLOCKED - needs unblocking
2026-01-23 | Team Bravo | John D. | PROJ-8702 | RTB - Blocked |  | 55292.12 | BLOCKED - needs unblocking
2026-01-23 | Team Charlie | Chris R. | PROJ-8636 | RTB - Blocked |  | 17680.04 | BLOCKED - needs unblocking
2026-01-26 | Team Alpha | Mike S. | PROJ-8771 | Ready To Build |  | 34258
2026-01-26 | Team Bravo | John D. | PROJ-8783 | RTB - Blocked |  | 33845.24 | BLOCKED - needs unblocking
2026-01-27 | No installs
2026-01-28 | No installs
2026-01-29 | No installs
2026-01-30 | No installs
2026-02-02 | No installs
2026-02-03 | No installs
2026-02-04 | No installs
2026-02-05 | No installs
2026-02-06 | No installs
2026-02-09 | No installs
2026-02-10 | No installs
2026-02-11 | No installs
2026-02-12 | No installs
2026-02-13 | No installs
2026-02-16 | No installs

## Centennial
Centennial - COMPLETE SCHEDULE
Crews: Team Delta (Dave M.), Team Echo (Steve L.)
Status: 1 RTB ¦ 15 Blocked ¦ 12 In Permitting
Date | Crew | Lead | Project | Stage | PE | Value | Notes
2026-01-19 | Team Delta | Dave M. | PROJ-7064 | RTB - Blocked |  | 39978 | BLOCKED - needs unblocking
2026-01-19 | Team Echo | Steve L. | PROJ-7035 | RTB - Blocked |  | 887388.82 | BLOCKED - needs unblocking
2026-01-20 | Team Delta | Dave M. | PROJ-7760 | RTB - Blocked |  | 40000 | BLOCKED - needs unblocking
2026-01-20 | Team Echo | Steve L. | PROJ-8618 | RTB - Blocked | YES | 33839.37 | BLOCKED - needs unblocking
2026-01-21 | Team Delta | Dave M. | PROJ-8650 | RTB - Blocked | YES | 56203.17 | BLOCKED - needs unblocking
2026-01-21 | Team Echo | Steve L. | PROJ-8295 | RTB - Blocked |  | 34455.12 | BLOCKED - needs unblocking
2026-01-22 | Team Delta | Dave M. | PROJ-8415 | RTB - Blocked |  | 16102.22 | BLOCKED - needs unblocking
2026-01-22 | Team Echo | Steve L. | PROJ-8694 | RTB - Blocked | YES | 30825.06 | BLOCKED - needs unblocking
2026-01-23 | Team Delta | Dave M. | PROJ-8677 | RTB - Blocked | YES | 41314.62 | BLOCKED - needs unblocking
2026-01-23 | Team Echo | Steve L. | PROJ-8535 | Ready To Build |  | 18291
2026-01-26 | Team Delta | Dave M. | PROJ-8528 | RTB - Blocked |  | 38479.73 | BLOCKED - needs unblocking
2026-01-26 | Team Echo | Steve L. | PROJ-8449 | RTB - Blocked |  | 33228 | BLOCKED - needs unblocking
2026-01-27 | Team Delta | Dave M. | PROJ-8724 | RTB - Blocked |  | 18291 | BLOCKED - needs unblocking
2026-01-27 | Team Echo | Steve L. | PROJ-8764 | RTB - Blocked |  | 14066.63 | BLOCKED - needs unblocking
2026-01-28 | Team Delta | Dave M. | PROJ-8409 | RTB - Blocked |  | 25851 | BLOCKED - needs unblocking
2026-01-28 | Team Echo | Steve L. | PROJ-8847 | RTB - Blocked |  | 23800.41 | BLOCKED - needs unblocking
2026-01-29 | No installs
2026-01-30 | No installs
2026-02-02 | No installs
2026-02-03 | No installs
2026-02-04 | No installs
2026-02-05 | No installs
2026-02-06 | No installs
2026-02-09 | No installs
2026-02-10 | No installs
2026-02-11 | No installs
2026-02-12 | No installs
2026-02-13 | No installs
2026-02-16 | No installs

## Colorado Spr
Colorado Springs - COMPLETE SCHEDULE
Crews: Team Foxtrot (Tom K.), Team Golf (Brian W.)
Status: 1 RTB ¦ 6 Blocked ¦ 6 In Permitting
Date | Crew | Lead | Project | Stage | PE | Value | Notes
2026-01-19 | Team Foxtrot | Tom K. | PROJ-8194 | RTB - Blocked | YES | 33837.15 | BLOCKED - needs unblocking
2026-01-19 | Team Golf | Brian W. | PROJ-8381 | RTB - Blocked | YES | 27402.53 | BLOCKED - needs unblocking
2026-01-20 | Team Foxtrot | Tom K. | PROJ-8660 | RTB - Blocked | YES | 30059.08 | BLOCKED - needs unblocking
2026-01-20 | Team Golf | Brian W. | PROJ-8524 | RTB - Blocked |  | 52251.61 | BLOCKED - needs unblocking
2026-01-21 | Team Foxtrot | Tom K. | PROJ-8723 | Ready To Build | YES | 33489.9
2026-01-21 | Team Golf | Brian W. | PROJ-8778 | RTB - Blocked | YES | 26837.91 | BLOCKED - needs unblocking
2026-01-22 | Team Foxtrot | Tom K. | PROJ-8794 | RTB - Blocked |  | 39174.69 | BLOCKED - needs unblocking
2026-01-23 | No installs
2026-01-26 | No installs
2026-01-27 | No installs
2026-01-28 | No installs
2026-01-29 | No installs
2026-01-30 | No installs
2026-02-02 | No installs
2026-02-03 | No installs
2026-02-04 | No installs
2026-02-05 | No installs
2026-02-06 | No installs
2026-02-09 | No installs
2026-02-10 | No installs
2026-02-11 | No installs
2026-02-12 | No installs
2026-02-13 | No installs
2026-02-16 | No installs

## San Luis Obi
San Luis Obispo - COMPLETE SCHEDULE
Crews: Team Hotel (Alex P.), Team India (Ryan T.)
Status: 9 RTB ¦ 9 Blocked ¦ 3 In Permitting
Date | Crew | Lead | Project | Stage | PE | Value | Notes
2026-01-19 | Team Hotel | Alex P. | PROJ-7367 | RTB - Blocked | YES | 12334 | BLOCKED - needs unblocking
2026-01-19 | Team India | Ryan T. | PROJ-7370 | Ready To Build | YES | 32950
2026-01-20 | Team Hotel | Alex P. | PROJ-7729 | RTB - Blocked | YES | 43621.6 | BLOCKED - needs unblocking
2026-01-20 | Team India | Ryan T. | PROJ-7292 | Ready To Build | YES | 21070
2026-01-21 | Team Hotel | Alex P. | PROJ-7932 | RTB - Blocked | YES | 41702.08 | BLOCKED - needs unblocking
2026-01-21 | Team India | Ryan T. | PROJ-8026 | RTB - Blocked | YES | 55000 | BLOCKED - needs unblocking
2026-01-22 | Team Hotel | Alex P. | PROJ-7963 | RTB - Blocked | YES | 38994.34 | BLOCKED - needs unblocking
2026-01-22 | Team India | Ryan T. | PROJ-8162 | RTB - Blocked | YES | 37146.9 | BLOCKED - needs unblocking
2026-01-23 | Team Hotel | Alex P. | PROJ-8217 | RTB - Blocked | YES | 52018.72 | BLOCKED - needs unblocking
2026-01-23 | Team India | Ryan T. | PROJ-7945 | Ready To Build |  | 28399.55
2026-01-26 | Team Hotel | Alex P. | PROJ-7981 | Ready To Build | YES | 12043.47
2026-01-26 | Team India | Ryan T. | PROJ-8634 | RTB - Blocked | YES | 37679.56 | BLOCKED - needs unblocking
2026-01-27 | Team Hotel | Alex P. | PROJ-6351 | RTB - Blocked |  | 60000 | BLOCKED - needs unblocking
2026-01-27 | Team India | Ryan T. | PROJ-8596 | Ready To Build |  | 36274
2026-01-28 | Team Hotel | Alex P. | PROJ-8762 | Ready To Build | YES | 25971.4
2026-01-28 | Team India | Ryan T. | PROJ-8540 | Ready To Build | YES | 42771.6
2026-01-29 | Team Hotel | Alex P. | PROJ-8632 | Ready To Build | YES | 24219
2026-01-29 | Team India | Ryan T. | PROJ-8846 | Ready To Build |  | 23800
2026-01-30 | No installs
2026-02-02 | No installs
2026-02-03 | No installs
2026-02-04 | No installs
2026-02-05 | No installs
2026-02-06 | No installs
2026-02-09 | No installs
2026-02-10 | No installs
2026-02-11 | No installs
2026-02-12 | No installs
2026-02-13 | No installs
2026-02-16 | No installs

## Camarillo
Camarillo - COMPLETE SCHEDULE
Crews: Team Juliet (Mark H.), Team Kilo (Jeff C.)
Status: 10 RTB ¦ 5 Blocked ¦ 1 In Permitting
Date | Crew | Lead | Project | Stage | PE | Value | Notes
2026-01-19 | Team Juliet | Mark H. | PROJ-7428 | RTB - Blocked |  | 22250 | BLOCKED - needs unblocking
2026-01-19 | Team Kilo | Jeff C. | PROJ-7756 | RTB - Blocked |  | 30325 | BLOCKED - needs unblocking
2026-01-20 | Team Juliet | Mark H. | PROJ-8091 | Ready To Build | YES | 63744.75
2026-01-20 | Team Kilo | Jeff C. | PROJ-8320 | RTB - Blocked |  | 10226.82 | BLOCKED - needs unblocking
2026-01-21 | Team Juliet | Mark H. | PROJ-8609 | Ready To Build | YES | 29944.34
2026-01-21 | Team Kilo | Jeff C. | PROJ-8656 | RTB - Blocked | YES | 62941.49 | BLOCKED - needs unblocking
2026-01-22 | Team Juliet | Mark H. | PROJ-8683 | Ready To Build | YES | 55767.89
2026-01-22 | Team Kilo | Jeff C. | PROJ-8697 | Ready To Build | YES | 18203.94
2026-01-23 | Team Juliet | Mark H. | PROJ-8466 | Ready To Build |  | 5600
2026-01-23 | Team Kilo | Jeff C. | PROJ-8472 | RTB - Blocked | YES | 30478 | BLOCKED - needs unblocking
2026-01-26 | Team Juliet | Mark H. | PROJ-8730 | Ready To Build | YES | 42966
2026-01-26 | Team Kilo | Jeff C. | PROJ-8749 | Ready To Build | YES | 29431.08
2026-01-27 | Team Juliet | Mark H. | PROJ-8810 | Ready To Build | YES | 18203.94
2026-01-27 | Team Kilo | Jeff C. | PROJ-8832 | Ready To Build | YES | 13198.8
2026-01-28 | Team Juliet | Mark H. | PROJ-8943 | Ready To Build |  | 2750
2026-01-29 | No installs
2026-01-30 | No installs
2026-02-02 | No installs
2026-02-03 | No installs
2026-02-04 | No installs
2026-02-05 | No installs
2026-02-06 | No installs
2026-02-09 | No installs
2026-02-10 | No installs
2026-02-11 | No installs
2026-02-12 | No installs
2026-02-13 | No installs
2026-02-16 | No installs