## PE Project Report
Project ID | Project Name | Location | AHJ | Utility | Project Type | Deal Value | Current Stage | Forecasted Install Date | Days to Install | Forecasted Inspection Date | Days to Inspection | Forecasted PTO Date | Days to PTO | Status | HubSpot Link
18872830551 | PROJ-7075 ¦ Miller, Jason ¦ 2315 S Monroe St, Denver, CO 80210 | Centennial | Denver | Xcel Energy | Battery;EV Charger;Solar | 72563.2 | Design | 2026-01-14 | -4 | 2025-01-16 | -366 | 2025-02-19 | -332 | OVERDUE
29502687648 | PROJ-7353 ¦ Frey, Robert ¦ 390 Porter Ranch Rd, Nederland, CO 80466 | Westminster | Boulder County | Xcel Energy | Battery;Solar | 30872.4 | Inspection | 2025-03-04 | -319 | 2025-04-13 | -279 | 2025-04-26 | -266 | OVERDUE
23041358644 | PROJ-7367 ¦ Chatham, Ken ¦ 1055 Tishlini Lane , Tempelton, CA 93465 | San Luis Obispo | SLO County | PG&E | Solar | 12334 | Inspection | 2025-02-05 | -346 | 2025-03-23 | -300 | 2025-04-27 | -265 | OVERDUE
28860087969 | PROJ-7370 ¦ Pelisek, Katie ¦ 1620 Geneseo Rd, Paso Robles, CA 93446 | San Luis Obispo | El Paso de Robles (Paso Robles) | PG&E | Battery;EV Charger | 32950 | Install Complete | 2025-02-20 | -331 | 2025-04-08 | -284 | 2025-05-04 | -258 | OVERDUE
33823251811 | PROJ-7729 ¦ Benson, Nancy ¦ 5385 Rancho La Loma Linda Dr, Paso Robles, CA 93446 | San Luis Obispo | SLO County | PG&E | Back Up Switch;Battery;Electrical;Solar;Solar Add-On | 43621.6 | Inspection | 2025-04-22 | -270 | 2025-06-07 | -224 | 2025-07-12 | -189 | OVERDUE
33719541677 | PROJ-7777 ¦ Slater, Jami ¦ 9700 Sugarloaf Rd, Boulder, CO 80302 | Westminster | Boulder County | Xcel Energy | Battery;Solar | 37194.8 | Inspection | 2025-06-09 | -222 | 2025-07-20 | -181 | 2025-08-02 | -168 | OVERDUE
28462208159 | PROJ-7292 ¦ Smith, Richard ¦ 34979 Sky Ranch Road, Carmel Valley, CA 93924 | San Luis Obispo | Monterey County | PG&E | Battery | 21070 | Install Complete | 2025-06-11 | -221 | 2025-07-26 | -175 | 2025-08-18 | -152 | OVERDUE
35133791026 | PROJ-7932 ¦ Frantz, John ¦ 5001 Lopez Dr, Arroyo Grande, CA 93420 | San Luis Obispo | SLO County | PG&E | Battery;EV Charger;Solar | 41702.08 | Inspection | 2025-06-17 | -214 | 2025-08-02 | -169 | 2025-09-06 | -134 | OVERDUE
35668319596 | PROJ-8026 ¦ Flores, Robert ¦ 6475 Mira Cielo, San Luis Obispo, CA 93401 | San Luis Obispo | San Luis Obispo County | PG&E | Back Up Switch;Battery;EV Charger;Solar | 55000 | Inspection | 2025-07-19 | -182 | 2025-08-31 | -139 | 2025-09-18 | -121 | OVERDUE
33821815854 | PROJ-7731 ¦ Chin, Alan ¦ 12555 Barley Hill Rd, Los Altos Hills, CA 94024 | San Luis Obispo | Los Altos Hills | SCE | Battery;Solar | 24092.96 | PTO Submitted | 2025-05-20 | -243 | 2025-07-29 | -172 | 2025-09-25 | -114 | OVERDUE
22337108294 | PROJ-8006 ¦ Yan Zhang, Hai ¦ 7 Benchmark Dr, Boulder, CO 80303 | Westminster | Boulder County | Xcel Energy | Battery;Solar | 32006.72 | Install Complete | 2025-08-10 | -160 | 2025-09-20 | -119 | 2025-10-03 | -106 | OVERDUE
38524620936 | PROJ-8162 ¦ Clayton, Dan ¦ 1548 Strand Way, Oceano, CA 93445 | San Luis Obispo | San Luis Obispo County | PG&E | Battery;EV Charger;Solar | 37146.9 | Inspection | 2025-08-15 | -155 | 2025-09-27 | -113 | 2025-10-15 | -94 | OVERDUE
38568935058 | PROJ-8194 ¦ Clement, Nick ¦ 708 Sahwatch Street, Colorado Springs, CO 80903 | Colorado Springs | Pikes Peak (PPRBD) | CSU | Battery;Solar | 33837.15 | Inspection | 2025-09-30 | -109 | 2025-10-18 | -91 | 2025-10-24 | -85 | OVERDUE
37116101470 | PROJ-7963 ¦ Jerkovich, Nick ¦ 2460 LAUREL AVE, Morro Bay, CA 93442 | San Luis Obispo | Morro Bay | PG&E | Battery;EV Charger;Roofing;Solar | 38994.34 | Inspection | 2025-08-13 | -157 | 2025-10-18 | -91 | 2025-10-31 | -78 | OVERDUE
36741931101 | PROJ-7981 ¦ Aguilar, JaKe ¦ 351 Panay st , Morro Bay, CA 93442 | San Luis Obispo | Morro Bay | PG&E | Solar | 12043.47 | Install Complete | 2025-08-19 | -151 | 2025-10-24 | -85 | 2025-11-06 | -72 | OVERDUE
39217639532 | PROJ-8217 ¦ Violetti, Joseph ¦ 2222 Richview Rd, Santa Maria, CA 93455 | San Luis Obispo | Santa Barbara County | PG&E | Battery;Solar | 52018.72 | Inspection | 2025-08-24 | -147 | 2025-10-13 | -96 | 2025-11-26 | -52 | OVERDUE
42444857716 | PROJ-8476 ¦ Dutra, Amanda ¦ 556 Via La Barranca, Arroyo Grande, CA 93420 | San Luis Obispo | Arroyo Grande | PG&E | Battery;EV Charger;Solar | 55264 | 22580872 | 2025-12-05 | -44 | 2025-11-06 | -72 | 2025-11-28 | -50 | OVERDUE | https://app.hubspot.com/contacts/21710069/record/0-3/42444857716?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
39611469681 | PROJ-8457 ¦ Gibson, Field ¦ Play Doe Lane, Paso Robles, CA 93446 | San Luis Obispo | San Luis Obispo County | PG&E | Battery;Solar | 49041.58 | Ready To Build | 2025-09-30 | -109 | 2025-11-12 | -67 | 2025-11-30 | -48 | OVERDUE
42860147536 | PROJ-8624 ¦ Stoll, Heather ¦ 1240 Quail Ridge Road, Solvang, CA 93463 | San Luis Obispo | Unknown | PG&E | Battery;Solar | 59491 | Install Scheduled | 2025-10-12 | -97 | 2025-11-17 | -61 | 2025-12-03 | -45 | OVERDUE | https://app.hubspot.com/contacts/21710069/record/0-3/42860147536?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
40983782672 | PROJ-8381 ¦ Gaalema, Steve ¦ 12930 Morris Trail, Colorado Springs, CO 80908 | Colorado Springs | El Paso County | MVEA | Battery;Solar | 27402.53 | Inspection | 2025-11-10 | -68 | 2025-11-28 | -50 | 2025-12-03 | -45 | OVERDUE | https://app.hubspot.com/contacts/21710069/record/0-3/40983782672?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
42265220259 | PROJ-8540 ¦ Norholm, Poul ¦ 301 Fair Oaks Ave, Arroyo Grande, CA 93420 | San Luis Obispo | Arroyo Grande | PG&E | Battery;EV Charger;Solar | 42771.6 | Install Complete | 2025-12-29 | -20 | 2025-11-12 | -66 | 2025-12-05 | -44 | OVERDUE | https://app.hubspot.com/contacts/21710069/record/0-3/42265220259?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
42828630669 | PROJ-8538 ¦ Newman, Korie ¦ 10600 Santa Rita rd, Cayucos, CA 93430 | San Luis Obispo | San Luis Obispo County | PG&E | Battery;EV Charger;Solar | 39984.04 | PTO Submitted | 2025-10-11 | -98 | 2025-11-22 | -56 | 2025-12-11 | -37 | OVERDUE | https://app.hubspot.com/contacts/21710069/record/0-3/42828630669?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43658515205 | PROJ-8741 ¦ McDonald, Carlotta ¦ 346 Emmons Rd, Cambria, CA 93428 | San Luis Obispo | San Luis Obispo County | PG&E | Battery;EV Charger;Solar | 18802.72 | 24743347 | 2025-11-20 | -59 | 2025-12-11 | -38 | 2025-12-18 | -31 | OVERDUE | https://app.hubspot.com/contacts/21710069/record/0-3/43658515205?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
38866623353 | PROJ-8091 ¦ Rakoski, Noah ¦ 20120 Wells Dr, Woodland Hills , CA 91364 | Camarillo | Los Angeles | LADWP | Back Up Switch;Battery;Solar | 63744.75 | Install Complete | 2025-08-23 | -148 | 2025-10-31 | -79 | 2025-12-19 | -29 | OVERDUE
12154128687 | PROJ-8618 ¦ Miller, Tamara ¦ 4145 Gray St, Wheat Ridge, CO 80212 | Centennial | Wheat Ridge | Xcel Energy | Battery;EV Charger;Solar | 33839.37 | Inspection | 2025-11-09 | -69 | 2025-12-20 | -28 | 2026-01-09 | -8 | OVERDUE
39210771611 | PROJ-8170 ¦ Levitt, Sol ¦ 4029 Via Laguna, Santa Barbara, CA 93110 | Camarillo | Santa Barbara | SCE | Battery;EV Charger;Roofing;Solar | 135084.81 | Install Scheduled | 2025-09-06 | -133 | 2025-11-15 | -63 | 2026-01-13 | -4 | OVERDUE
43216836975 | PROJ-8654 ¦ Lingle, Sam ¦ 13825 Overlook Pl, Colorado Springs, CO 80921 | Colorado Springs | El Paso County | MVEA | Battery | 28728 | 22580872 | 2026-01-05 | -13 | 2026-01-14 | -3 | 2026-01-19 | 2 | Due Soon | https://app.hubspot.com/contacts/21710069/record/0-3/43216836975?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
45105028218 | PROJ-8740 ¦ Guiltinan, Jeff ¦ 1305 Newport Ave, Arroyo Grande, CA 93420 | San Luis Obispo | Arroyo Grande | PG&E | Battery;EV Charger;Solar;Electrical | 37403.08 | Ready To Build | 2025-11-11 | -67 | 2026-01-01 | -16 | 2026-01-23 | 6 | Due Soon | https://app.hubspot.com/contacts/21710069/record/0-3/45105028218?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48169229828 | PROJ-8800 ¦ Ditmanson, Mark ¦ 1277 Castro Rd., Monterey, CA 93940 | San Luis Obispo | Unknown | PG&E | Back Up Switch;Battery;Solar | 74252.67 | Permit Issued | 2025-12-09 | -39 | 2026-01-14 | -4 | 2026-01-29 | 12 | Due Soon | https://app.hubspot.com/contacts/21710069/record/0-3/48169229828?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
45151434504 | PROJ-8723 ¦ Baker, Bradley ¦ 12460 Woodruff Dr, Colorado Springs, CO 80921 | Colorado Springs | Pikes Peak (PPRBD) | CSU | Battery;Solar | 33489.9 | Install Complete | 2026-01-05 | -12 | 2026-01-23 | 6 | 2026-01-29 | 12 | Due Soon | https://app.hubspot.com/contacts/21710069/record/0-3/45151434504?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43487863931 | PROJ-8650 ¦ Rosell, Sean ¦ 933 Xenon Ct, Golden, CO 80401 | Centennial | Jefferson County | Xcel Energy | Battery;Solar | 56203.17 | Inspection | 2025-12-04 | -44 | 2026-01-06 | -11 | 2026-01-29 | 12 | Due Soon | https://app.hubspot.com/contacts/21710069/record/0-3/43487863931?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43125493794 | PROJ-8642 ¦ Hart, Roger Terence ¦ 1234 Doris Cir, Erie, CO 80516 | Westminster | Weld County | United Power, Inc. | Battery;Solar | 63792.64 | Inspection | 2025-12-12 | -36 | 2026-01-17 | -1 | 2026-01-29 | 12 | Due Soon | https://app.hubspot.com/contacts/21710069/record/0-3/43125493794?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43562208539 | PROJ-8634 ¦ Bryan, Jake ¦ 4691 Tepusquet Rd, Santa Maria, CA 93454 | San Luis Obispo | Santa Barbara County | PG&E | Battery;EV Charger;Electrical;Solar | 37679.56 | Inspection | 2025-10-29 | -80 | 2025-12-19 | -29 | 2026-02-01 | 15 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/43562208539?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48277044338 | PROJ-8811 ¦ Hall, Wayne ¦ 3255 Ryan Rd, Creston, CA 93432 | San Luis Obispo | Unknown | PG&E | Battery;Solar | 36566.11 | Permit Issued | 2025-12-13 | -35 | 2026-01-18 | 1 | 2026-02-03 | 16 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/48277044338?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43067096885 | PROJ-8743 ¦ Gantman, Marissa ¦ 2309 Watersong Cir, Longmont, CO 80504 | Westminster | Longmont | Longmont | Solar | 16743.65 | Inspection | 2025-12-28 | -20 | 2026-01-31 | 14 | 2026-02-03 | 17 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/43067096885?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48893857114 | PROJ-8830 ¦ Wagner, Kelsey ¦ 315 S Mason St, Arroyo Grande, CA 93420 | San Luis Obispo | Unknown | PG&E | Battery;Solar | 26818 | 20461935 | 2025-12-17 | -32 | 2026-01-21 | 4 | 2026-02-06 | 20 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/48893857114?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43784573251 | PROJ-8694 ¦ Morales, Michelle ¦ 11542 W Lake Dr, Littleton, CO 80127 | Centennial | Jefferson County | Xcel Energy | Battery;Electrical;Solar | 30825.06 | Inspection | 2025-12-13 | -35 | 2026-01-15 | -2 | 2026-02-07 | 21 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/43784573251?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
40892008480 | PROJ-8660 ¦ Seidle, Nathan ¦ 2779 River Drive, Alma, CO 80420 | Colorado Springs | Park County | Xcel Energy | Battery;Solar | 30059.08 | Inspection | 2025-12-09 | -39 | 2026-01-13 | -4 | 2026-02-08 | 22 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/40892008480?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
49472329890 | PROJ-8843 ¦ Londono, Juan ¦ 753 Guy Turner, Camarillo, CA 93010 | Camarillo | Unknown | SCE | Battery | 18291 | Permit Submitted | 2025-12-21 | -27 | 2026-01-26 | 9 | 2026-02-11 | 25 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/49472329890?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
41519729833 | PROJ-8677 ¦ SHAY, BENJAMIN ¦ 134 S Pontiac St, Denver, CO 80230 | Centennial | Denver | Xcel Energy | Battery;Solar | 41314.62 | Inspection | 2025-12-17 | -31 | 2026-01-08 | -9 | 2026-02-11 | 25 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/41519729833?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43711803674 | PROJ-8686 ¦ Maddox, Glenn ¦ 9083 Sheridan Loop, Salida, CO 81201 | Colorado Springs | Chaffee County | Xcel Energy | Battery;Solar | 42314.62 | Ready To Build | 2025-12-15 | -33 | 2026-01-19 | 2 | 2026-02-14 | 28 | On Track | https://app.hubspot.com/contacts/21710069/record/0-3/43711803674?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
28809813653 | PROJ-8762 ¦ Ellis, David ¦ 11295 Los Osos Valley Rd #27, San Luis Obispo, CA 93405 | San Luis Obispo | San Luis Obispo | PG&E | Battery;Solar | 25971.4 | Install Complete | 2025-12-05 | -43 | 2026-01-12 | -5 | 2026-02-16 | 30 | On Track
44027054617 | PROJ-8752 ¦ Davis, Glynn ¦ 5665 Encima Ct, Atascadero, CA 93422 | San Luis Obispo | Atascadero | PG&E | Battery;Solar;Roofing | 39461.18 | Ready To Build | 2025-12-26 | -22 | 2026-01-30 | 13 | 2026-02-22 | 36 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/44027054617?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
42027887227 | PROJ-8450 ¦ Khalilzadeh, Afshin ¦ 25335 Prado De Los Gansos, Calabasas, CA 91302 | Camarillo | City of Calabasas | SCE | Back Up Switch;Battery;Roofing;Solar | 94561.91 | Ready To Build | 2025-10-20 | -89 | 2025-12-29 | -19 | 2026-02-26 | 40 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/42027887227?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48425963637 | PROJ-8812 ¦ Ammon, Thomas ¦ 1722 BEE CANYON RD, Arroyo Grande, CA 93420 | San Luis Obispo | San Luis Obispo County | PG&E | Battery;Back Up Switch | 32124 | Design | 2026-01-15 | -3 | 2026-02-08 | 22 | 2026-02-27 | 41 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48425963637?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
46572128347 | PROJ-8781 ¦ Pierce, Carol ¦ 1761 Paradise Meadows Lane , Templeton, CA 93465 | San Luis Obispo | SLO County | PG&E | Battery;Solar | 28648.83 | Install Scheduled | 2025-12-08 | -40 | 2026-01-23 | 5 | 2026-02-27 | 40 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/46572128347?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
46048497773 | PROJ-8778 ¦ Rees, Christiaan ¦ 18470 Academy Cir, Monument, CO 80132 | Colorado Springs | El Paso County | MVEA | Solar | 26837.91 | Inspection | 2026-02-06 | 20 | 2026-02-24 | 38 | 2026-03-01 | 43 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/46048497773?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
41564768293 | PROJ-8472 ¦ Heiting, Craig ¦ 32000 Watergate Court, Westlake Village, CA 91361 | Camarillo | City of Westlake Village | SCE | Battery;Back Up Switch | 30478 | Inspection | 2025-12-15 | -34 | 2026-01-03 | -14 | 2026-03-03 | 45 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/41564768293?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
46256518952 | PROJ-8754 ¦ Kyu Park, Byung ¦ 4237 Lantana Ct, Santa Maria, CA 93455 | San Luis Obispo | Santa Barbara County | PG&E | Battery;EV Charger;Solar;Back Up Switch | 52822.88 | Permit Issued | 2025-12-02 | -46 | 2026-01-22 | 5 | 2026-03-07 | 49 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/46256518952?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48488136580 | PROJ-8823 ¦ Thompson, Cliff ¦ 358 N Court St, Baywood-Los Osos, CA 93402 | San Luis Obispo | SLO County | PG&E | Battery | 20109.6 | 22580872 | 2025-12-12 | -37 | 2026-02-08 | 22 | 2026-03-15 | 57 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48488136580?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
42755755408 | PROJ-8609 ¦ Case, Jared ¦ 367 Nueve Ct, Camarillo, CA 93012 | Camarillo | City of Camarillo | SCE | Back Up Switch;Battery;Solar | 29944.34 | Install Complete | 2025-11-12 | -66 | 2026-01-21 | 4 | 2026-03-21 | 63 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/42755755408?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48512075589 | PROJ-8880 ¦ Bethel, Barbara ¦ 1111 Long View , Pismo Beach, CA 93449 | San Luis Obispo | Pismo Beach | PG&E | Solar | 10469.34 | Permit Submitted | 2026-01-26 | 8 | 2026-03-02 | 44 | 2026-03-26 | 68 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48512075589?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53131630629 | PROJ-8930 ¦ Kuhlmann, Kurt ¦ 295 Via Piedras Blancas, san simeon, CA 93452 | San Luis Obispo | Unknown | PG&E | Back Up Switch;Battery;Solar | 49673.39 | Permit Issued | 2026-02-07 | 21 | 2026-03-15 | 57 | 2026-03-31 | 73 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53131630629?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43878057266 | PROJ-8656 ¦ L Tansey, Kevin ¦ 2771 Acacia St, Camarillo, CA 93012 | Camarillo | City of Camarillo | SCE | Back Up Switch;Battery;Electrical;Solar | 62941.49 | Inspection | 2025-11-24 | -54 | 2026-02-02 | 16 | 2026-04-02 | 74 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/43878057266?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52345682436 | Wendel, Doug ¦ 4181 Niblick Dr, Longmont, CO 80503 | Westminster | Unknown | Xcel Energy | Battery;Solar | 68715.92 | PTO Complete | 2026-02-11 | 24 | 2026-03-18 | 60 | 2026-04-03 | 76 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52345682436?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
45716506670 | PROJ-8851 ¦ Atkinson, Pamela Meyla ¦ 5260 Chauplin Ave, Atascadero, CA 93422 | San Luis Obispo | Atascadero | PG&E | Battery;Solar | 53309.36 | Permit Issued | 2026-02-04 | 18 | 2026-03-11 | 53 | 2026-04-03 | 76 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/45716506670?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
51930719144 | PROJ-8883 ¦ Nenow, Andrea ¦ 393 Eric Lane, Templeton, CA 93465 | San Luis Obispo | San Luis Obispo County | PG&E | Back Up Switch;Battery;EV Charger;Solar;Roofing | 38478.92 | Permit Issued | 2026-02-02 | 16 | 2026-03-16 | 58 | 2026-04-04 | 77 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51930719144?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52342352176 | PROJ-8976 ¦ Macchi, C.R. ¦ 17085 W 62nd Cir, Golden, CO 80403 | Centennial | Unknown | Xcel Energy | Battery | 18291 | Permit Submitted | 2026-02-14 | 28 | 2026-03-22 | 64 | 2026-04-07 | 80 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52342352176?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
42969550992 | PROJ-8632 ¦ Johnston, Jeanette ¦ Santa Fe 2nd NW of Ocean Ave, Carmel, CA 93921 | San Luis Obispo | Monterey County | PG&E | Battery;Solar | 24219 | Install Complete | 2025-12-21 | -27 | 2026-03-15 | 57 | 2026-04-07 | 80 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/42969550992?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43817717324 | PROJ-8683 ¦ Richards, Amy M ¦ 645 Skyline Rd, Ventura, CA 93003 | Camarillo | Ventura County | SCE | Back Up Switch;Battery;Solar | 55767.89 | Install Complete | 2025-11-30 | -48 | 2026-02-08 | 22 | 2026-04-08 | 81 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/43817717324?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53999169648 | PROJ-8999 ¦ Lyons, Ella ¦ 1710 Utah St, Golden, CO 80401 | Centennial | Unknown | Xcel Energy | Battery | 19026 | Permit Submitted | 2026-02-17 | 31 | 2026-03-25 | 66 | 2026-04-09 | 82 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53999169648?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53561556257 | PROJ-9005 ¦ Cruz Jr, Alcidez ¦ 17910 slavin way, Platteville, CO 80651 | Westminster | Unknown | Xcel Energy | Battery;Solar | 46004.14 | Permit Submitted | 2026-02-18 | 31 | 2026-03-25 | 67 | 2026-04-10 | 83 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53561556257?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
39669410607 | PROJ-8641 ¦ Liu, Wei ¦ 25380 Quail Summit Lane, Monterey, CA 93940 | San Luis Obispo | Monterey County | PG&E | Back Up Switch;Battery;Solar;Roofing | 66061.1 | Permit Submitted | 2025-12-24 | -24 | 2026-03-18 | 60 | 2026-04-10 | 83 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/39669410607?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43946261506 | PROJ-8697 ¦ Castillo, David ¦ 1878 Hobart Drive, Camarillo, CA 93010 | Camarillo | City of Camarillo | SCE | Back Up Switch;Battery | 18203.94 | Install Complete | 2025-12-03 | -45 | 2026-02-11 | 25 | 2026-04-11 | 84 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/43946261506?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52610867858 | PROJ-8910 ¦ Tullius, Jami ¦ 5220 Topaz Dr, Colorado Springs, CO 80918 | Colorado Springs | Pikes Peak (PPRBD) | CSU | Solar | 28599.58 | 20461935 | 2026-03-27 | 69 | 2026-04-14 | 87 | 2026-04-20 | 93 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52610867858?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52479200092 | PROJ-8909 ¦ Sekelsky, Kristin ¦ 6552 Courtland Place, Colorado Springs, CO 80924 | Colorado Springs | Pikes Peak (PPRBD) | CSU | Battery;Solar | 72102.8 | Ready To Build | 2026-03-29 | 71 | 2026-04-16 | 89 | 2026-04-22 | 95 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52479200092?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52037859506 | PROJ-8884 ¦ Davis, John ¦ 631 Huajatolla Valley Estates Dr, La Veta, CO 81055 | Colorado Springs | Huerfano County | SIEA | Solar | 26932.64 | Permit Issued | 2026-03-20 | 61 | 2026-04-17 | 90 | 2026-04-23 | 96 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52037859506?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
45369375558 | PROJ-8730 ¦ Diep, Jason ¦ 2277 El Nido Ct, Camarillo, CA 93010 | Camarillo | City of Camarillo | SCE | Back Up Switch;Battery;Solar | 42966 | Install Complete | 2025-12-16 | -32 | 2026-02-24 | 38 | 2026-04-24 | 97 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/45369375558?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
51931621262 | PROJ-8904 ¦ Sobrevilla, Saidel ¦ 8661 Hunters Hill Ln , Littleton, CO 80125 | Centennial | Douglas County | Xcel Energy | Battery;Solar | 83114.94 | Permit Issued | 2026-03-09 | 51 | 2026-04-10 | 83 | 2026-04-26 | 99 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51931621262?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
51956310800 | PROJ-8903 ¦ Martinez, Ricardo ¦ 8727 Hunters Hill Ln, Littleton, CO 80125 | Centennial | Douglas County | Xcel Energy | Battery;Solar | 49239.88 | Permit Issued | 2026-03-09 | 51 | 2026-04-10 | 83 | 2026-04-26 | 99 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51956310800?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
45934137926 | PROJ-8749 ¦ Casselman, David ¦ 27002 Malibu Cove Colony Dr, Malibu, CA 90265 | Camarillo | Malibu | SCE | Battery;Back Up Switch | 29431.08 | Install Complete | 2025-12-22 | -26 | 2026-03-03 | 44 | 2026-04-30 | 103 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/45934137926?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52390853461 | PROJ-8911 ¦ Varghese, Julian ¦ 7420 Mount Meeker Road, Longmont, CO 80503 | Westminster | Boulder County | Xcel Energy | Battery | 18291 | Permit Submitted | 2026-03-14 | 56 | 2026-04-23 | 96 | 2026-05-07 | 109 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52390853461?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
46447596822 | PROJ-8767 ¦ Smallwood, Brian ¦ 2809 Acacia St, Camarillo, CA 93012 | Camarillo | City of Camarillo | SCE | Back Up Switch;Battery;Solar | 44891.75 | PTO Submitted | 2025-12-29 | -19 | 2026-03-09 | 51 | 2026-05-07 | 110 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/46447596822?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53630691648 | PROJ-8974 ¦ Wehner, Chad ¦ 4630 Topaz Dr, Colorado Springs, CO 80918 | Colorado Springs | El Paso County | CSU | Battery;Solar | 41855.67 | Permit Issued | 2026-04-08 | 81 | 2026-05-10 | 113 | 2026-05-08 | 111 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53630691648?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
50895749181 | Pyziak, David M ¦ 4229 Captain Jack Ln, Colorado Springs, CO 80924 | Colorado Springs | Pikes Peak (PPRBD) | CSU | Battery;Electrical;Solar | 59955.56 | PTO Complete | 2026-04-14 | 87 | 2026-05-02 | 105 | 2026-05-08 | 111 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/50895749181?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52384418094 | PROJ-8905 ¦ Pearson, LESLIE ¦ 5352 Devils Head Cir, Golden, CO 80403 | Centennial | Jefferson County | Xcel Energy | Battery;Solar | 26522.12 | Permit Submitted | 2026-03-18 | 60 | 2026-04-20 | 93 | 2026-05-13 | 116 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52384418094?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52071909996 | PROJ-8915 ¦ Sjostrom, Bradley ¦ 22568 Westview Ave, Golden, CO 80401 | Centennial | Jefferson County | Xcel Energy | Battery | 18291 | Permit Issued | 2026-03-19 | 61 | 2026-04-21 | 94 | 2026-05-14 | 117 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52071909996?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53412268712 | PROJ-8952 ¦ Blondeau, Donna ¦ 8780 Skyland Dr, Longmont, CO 80503 | Westminster | Boulder County | Xcel Energy | Battery | 28728 | Permit Submitted | 2026-03-24 | 66 | 2026-05-03 | 106 | 2026-05-16 | 119 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53412268712?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52883875648 | PROJ-8907 ¦ Fitch, Aide ¦ 993 Arapahoe Cir, Louisville, CO 80027 | Westminster | Louisville | Xcel Energy | Battery;Solar | 47135.92 | Permit Submitted | 2026-03-21 | 63 | 2026-04-21 | 94 | 2026-05-16 | 119 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52883875648?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
11761029909 | PROJ-8955 ¦ Lu, Cheng-Hsuan ¦ 4569 S Meadow Dr, Boulder, CO 80301 | Westminster | Boulder County | Xcel Energy | Battery;EV Charger | 33250.8 | Permit Issued | 2026-03-24 | 66 | 2026-05-03 | 106 | 2026-05-17 | 119 | Scheduled
52833472822 | PROJ-8914 ¦ Coombs, Michael ¦ 5734 Pinon Dr, Elizabeth, CO 80107 | Centennial | Elbert County | IREA | Battery;Solar | 60259.1 | Permit Issued | 2026-03-30 | 72 | 2026-05-06 | 109 | 2026-05-19 | 122 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52833472822?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52244751445 | PROJ-8908 ¦ Martin, Edward ¦ 155 Southmoor Dr, Denver, CO 80220 | Centennial | Denver | Xcel Energy | Battery | 32844 | Permit Issued | 2026-03-25 | 67 | 2026-04-16 | 89 | 2026-05-20 | 123 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52244751445?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
47325983380 | PROJ-8797 ¦ Feeney, Patrick ¦ 4641 Pepper Mill St, Moorpark, CA 93021 | Camarillo | City of Moorpark | SCE | Back Up Switch;Battery;Solar | 34524.5 | Permit Issued | 2026-01-12 | -5 | 2026-03-23 | 65 | 2026-05-21 | 124 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/47325983380?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
49708527886 | PROJ-8937 ¦ Pratsch, Eric ¦ 15483 W 51st Pl, Golden, CO 80403 | Centennial | Jefferson County | Xcel Energy | Solar;Battery | 36498.72 | Permit Issued | 2026-03-27 | 69 | 2026-04-29 | 102 | 2026-05-22 | 125 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/49708527886?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48830868904 | PROJ-8838 ¦ Simpkins, James ¦ 23129 Erwin St, Woodland Hills, CA 91367 | Camarillo | Los Angeles County | LADWP | Back Up Switch;Battery | 17768.4 | Permit Submitted | 2026-01-25 | 8 | 2026-04-04 | 77 | 2026-05-23 | 126 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48830868904?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
20720050747 | PROJ-8947 ¦ Hellner, Richard ¦ 19770 W 57th Lane, Golden, CO 80403 | Centennial | Jefferson County | Xcel Energy | Solar;Battery | 53743.47 | Permit Issued | 2026-03-28 | 70 | 2026-05-01 | 103 | 2026-05-23 | 126 | Scheduled
42826488415 | PROJ-8929 ¦ Landrum, Adam ¦ 358 Mulberry Cir, Broomfield, CO 80020 | Westminster | Broomfield | Xcel Energy | Solar | 21723.05 | Permit Submitted | 2026-03-10 | 52 | 2026-05-01 | 104 | 2026-05-25 | 128 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/42826488415?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52607086402 | PROJ-8928 ¦ Schraad, Daryl ¦ 425 sawmill creek road, Evergreen, CO 80439 | Centennial | Clear Creek County | IREA | Battery;Solar | 48576 | Permit Issued | 2026-04-07 | 80 | 2026-05-14 | 116 | 2026-05-26 | 129 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52607086402?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48475133869 | PROJ-8810 ¦ Rahane, Annasaheb ¦ 194 Rose St, Fillmore, CA 93015 | Camarillo | City of Fillmore | SCE | Back Up Switch;Battery | 18203.94 | Install Complete | 2026-01-17 | 0 | 2026-03-28 | 70 | 2026-05-26 | 129 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48475133869?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
43910946823 | PROJ-8785 ¦ Hobbs, Jeff ¦ 13762 Center St, Carmel Valley, CA 93924 | San Luis Obispo | Monterey County | PG&E | Battery;Solar | 39287.87 | Install Scheduled | 2026-02-08 | 22 | 2026-05-03 | 106 | 2026-05-26 | 129 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/43910946823?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53501152385 | PROJ-8979 ¦ Koken, Daniel ¦ 1357 Gold Mine Ln, Evergreen, CO 80439 | Centennial | Jefferson County | Xcel Energy | Battery | 28728 | Permit Submitted | 2026-04-01 | 74 | 2026-05-04 | 107 | 2026-05-27 | 130 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53501152385?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53131685682 | PROJ-8966 ¦ HAYCRAFT, JEANNIE ¦ 16691 w 55th pl, golden, CO 80403 | Centennial | Jefferson County | Xcel Energy | Battery;EV Charger | 20113.8 | Permit Submitted | 2026-04-01 | 74 | 2026-05-04 | 107 | 2026-05-27 | 130 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53131685682?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52865379253 | Packer, Bill ¦ 951 Sunflower Street, Louisville, CO, USA, Louisville, CO 80027 | Westminster | Louisville | Xcel Energy | Battery;Solar | 53337.25 | PTO Complete | 2026-03-31 | 73 | 2026-05-01 | 104 | 2026-05-27 | 129 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52865379253?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48886868240 | PROJ-8819 ¦ Narang, Mukesh ¦ 489 Marymount Ct , Ventura , CA 93003 | Camarillo | Ventura | SCE | Back Up Switch;Battery;Solar | 35637 | Permit Submitted | 2026-01-18 | 1 | 2026-03-29 | 71 | 2026-05-27 | 130 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48886868240?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48816887137 | PROJ-8818 ¦ Falkenhagen, Scott ¦ 23565 Park Belmonte, Calabasas, CA 91302-1702 | Camarillo | City of Calabasas | SCE | Battery | 48851 | Permit Submitted | 2026-01-18 | 1 | 2026-03-29 | 71 | 2026-05-27 | 130 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48816887137?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48171013491 | PROJ-8815 ¦ Sorensen, Paul ¦ 4220 Mariposa Dr , Santa Barbara, CA 93110 | Camarillo | Santa Barbara | SCE | Back Up Switch;Battery;EV Charger;Solar | 33821.04 | Permit Submitted | 2026-01-18 | 1 | 2026-03-29 | 71 | 2026-05-27 | 130 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48171013491?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
29775766932 | PROJ-8975 ¦ Gawrych, Liliya ¦ 6996 Skunk Alley, Evergreen, CO 80439 | Centennial | Jefferson County | Xcel Energy | Battery | 29349.95 | Permit Issued | 2026-04-01 | 74 | 2026-05-04 | 107 | 2026-05-27 | 130 | Scheduled
17694760719 | Himmel, Evan ¦ 17769 W 95th Pl, Arvada, CO 80007 | Westminster | Jefferson County | Xcel Energy | Battery | 28728 | PTO Complete | 2026-04-01 | 74 | 2026-05-05 | 108 | 2026-05-27 | 130 | Scheduled
53290804084 | PROJ-8925 ¦ Bailey, Christine ¦ 2002 W 32nd St, Pueblo, CO 81008 | Colorado Springs | Pueblo | Black Hills | Battery | 18715.28 | Permit Issued | 2026-03-19 | 61 | 2026-04-24 | 96 | 2026-05-29 | 132 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53290804084?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53278160475 | PROJ-8924 ¦ McNeil, Jessie ¦ 4029 Hillside Dr, Pueblo, CO 81008 | Colorado Springs | Pueblo | Black Hills | Solar | 40656 | Permit Issued | 2026-03-19 | 61 | 2026-04-24 | 96 | 2026-05-29 | 132 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53278160475?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52836777632 | PROJ-8987 ¦ SKIGEN, SARAH ¦ 14905 W 54th Ave, Golden, CO 80403 | Centennial | Jefferson County | Xcel Energy | Battery | 18291 | Permit Submitted | 2026-04-03 | 76 | 2026-05-06 | 109 | 2026-05-29 | 132 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52836777632?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
48946535507 | PROJ-8824 ¦ Hillard, Mary Sue ¦ 1891 Lakehurst Avenue, Camarillo, CA 93010-3827 | Camarillo | City of Camarillo | SCE | Back Up Switch;Battery | 17768.4 | Permit Submitted | 2026-01-20 | 3 | 2026-03-31 | 73 | 2026-05-29 | 132 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/48946535507?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
11759540266 | PROJ-8935 ¦ Rooney, Chelsea ¦ 80 Defrance Way, Golden, CO 80401 | Centennial | Golden | Xcel Energy | Solar;Battery | 42773.91 | Permit Issued | 2026-03-29 | 71 | 2026-05-03 | 106 | 2026-05-29 | 132 | Scheduled
51728745368 | PROJ-8946 ¦ Plunkett, Cris ¦ 517 Venus Ave., Lompoc, CA 93436 | San Luis Obispo | Santa Barbara County | PG&E | Battery | 20109.6 | Permit Submitted | 2026-02-25 | 38 | 2026-04-16 | 89 | 2026-05-30 | 133 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51728745368?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
49134683809 | PROJ-8832 ¦ Harris, Robert ¦ 669 Larchmont St , Simi Valley , CA 93065 | Camarillo | Simi Valley | SCE | Battery | 13198.8 | Install Complete | 2026-01-21 | 4 | 2026-04-01 | 74 | 2026-05-30 | 133 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/49134683809?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
46676373629 | PROJ-8945 ¦ Whittemore, Todd ¦ 35471 Hidden Mesa Drive, Pueblo, CO 81006 | Colorado Springs | Pueblo County | Black Hills | Solar;Battery | 49899.48 | Permit Submitted | 2026-03-29 | 71 | 2026-04-28 | 101 | 2026-06-01 | 135 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/46676373629?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
49152858025 | PROJ-8840 ¦ Jasechko, Scott ¦ 7097 scripps crescent, goleta, CA 93117 | Camarillo | Goleta | SCE | Back Up Switch;Battery | 17768.4 | Permit Issued | 2026-01-25 | 8 | 2026-04-05 | 78 | 2026-06-03 | 137 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/49152858025?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
51953666487 | PROJ-8972 ¦ Xu, Sarah ¦ 3289 S Eudora St, Denver, CO 80222 | Centennial | Denver | Xcel Energy | Battery;Solar | 52584.14 | Permit Submitted | 2026-04-09 | 82 | 2026-05-01 | 104 | 2026-06-04 | 138 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51953666487?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53782899356 | Nuccio, Vito ¦ 15506 W Vassar Ave, Denver, CO 80228 | Centennial | Unknown | Xcel Energy | Battery | 18291 | qualifiedtobuy | 2026-04-02 | 75 | 2026-05-11 | 114 | 2026-06-05 | 139 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53782899356?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52918916683 | Gangadhar, Akshata ¦ 724 Via Arroyo, Ventura , CA 93003 | Camarillo | Unknown | SCE | Battery;Back Up Switch | 0 | qualifiedtobuy | 2026-04-02 | 75 | 2026-05-11 | 114 | 2026-06-05 | 139 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52918916683?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52316057972 | Schlander, Mark ¦ 330 Oakwood Pl, Boulder, CO 80304 | Westminster | Unknown | Xcel Energy | Battery;Solar | 34892.42 | Closed Won | 2026-04-02 | 75 | 2026-05-11 | 114 | 2026-06-05 | 139 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52316057972?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
51437855035 | Pratsch, Eric ¦ 15483 W 51st Pl, Golden, CO 80403 | Centennial | Jefferson County | Xcel Energy | Battery;EV Charger;Solar | 0 | qualifiedtobuy | 2026-04-02 | 75 | 2026-05-11 | 114 | 2026-06-05 | 139 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51437855035?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
28708917322 | Hansen, Gregory ¦ 3235 10th Street, Boulder, CO 80304 | Westminster | Unknown | Xcel Energy | Battery | 35490 | Closed Won | 2026-04-02 | 75 | 2026-05-11 | 114 | 2026-06-05 | 139 | Scheduled
52228146290 | PROJ-8994 ¦ Martin, Philip ¦ 6318 Oakwood Ct, Loveland, CO 80538 | Westminster | Larimer County | Xcel Energy | Battery | 18291 | Permit Submitted | 2026-04-07 | 79 | 2026-05-11 | 114 | 2026-06-06 | 140 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52228146290?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52106295185 | PROJ-8993 ¦ Vanatt, Trulane ¦ 15298 W Baker Ave, Lakewood, CO 80228 | Centennial | Lakewood | Xcel Energy | Battery | 18291 | Permit Submitted | 2026-04-09 | 82 | 2026-05-20 | 123 | 2026-06-10 | 144 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52106295185?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
15941713193 | PROJ-8934 ¦ Beckett, William ¦ 13117 W 73rd Lane , Arvada, CO 80005 | Westminster | Arvada | Xcel Energy | Battery | 28728 | Permit Submitted | 2026-04-05 | 78 | 2026-05-20 | 123 | 2026-06-10 | 144 | Scheduled
53527775873 | PROJ-8995 ¦ Trifon, Lisa ¦ 3715 Longwood Ave, Boulder, CO 80305 | Westminster | Boulder | Xcel Energy | Battery | 32844 | Permit Submitted | 2026-04-16 | 89 | 2026-05-27 | 130 | 2026-06-11 | 145 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53527775873?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
51527015294 | PROJ-8942 ¦ Zito, Heather ¦ 16594 W 93rd Way, Arvada, CO 80007 | Westminster | Arvada | Xcel Energy | Battery;Solar | 35725.29 | Permit Submitted | 2026-04-07 | 80 | 2026-05-22 | 125 | 2026-06-12 | 146 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51527015294?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
47284182065 | PROJ-8957 ¦ Reinicke, Nick ¦ 7180 Van Gordon Street, Arvada, CO 80004 | Westminster | Arvada | Xcel Energy | Solar | 20968.24 | Permit Submitted | 2026-04-07 | 80 | 2026-05-22 | 125 | 2026-06-12 | 146 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/47284182065?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53548594469 | PROJ-8978 ¦ Anderson, Jason ¦ 12916 W 61st Cir, Arvada, CO 80004 | Westminster | Arvada | Xcel Energy | Battery | 18291 | Permit Issued | 2026-04-11 | 84 | 2026-05-26 | 129 | 2026-06-16 | 150 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53548594469?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
51269373207 | PROJ-8869 ¦ Temesvary, Frank ¦ 31579 Sea Level Drive, Malibu, CA 90265 | Camarillo | Malibu | SCE | Back Up Switch;Battery;Solar | 32264.5 | PTO Submitted | 2026-02-16 | 30 | 2026-04-27 | 100 | 2026-06-25 | 159 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51269373207?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52230534414 | PROJ-8898 ¦ Psaros, Paris ¦ 7758 Jenna Dr, Goleta, CA 93117 | Camarillo | Goleta | SCE | Back Up Switch;Battery;EV Charger;Solar | 28258.15 | Permit Submitted | 2026-03-01 | 43 | 2026-05-10 | 113 | 2026-07-08 | 172 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52230534414?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
52678381440 | PROJ-8919 ¦ Smith, Adrian ¦ 106 Golden Glen Drive, Simi Valley, CA 93065 | Camarillo | Simi Valley | SCE | Back Up Switch;Battery;Roofing;Solar | 49051.46 | Permit Submitted | 2026-03-09 | 51 | 2026-05-18 | 121 | 2026-07-16 | 180 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/52678381440?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
51999614547 | Landis, Vance ¦ 46304 Pfeiffer Ridge Road, Big Sur, CA 93920 | San Luis Obispo | Monterey County | PG&E | Battery;EV Charger | 38133 | PTO Complete | 2026-04-02 | 75 | 2026-06-25 | 159 | 2026-07-18 | 182 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/51999614547?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53515443885 | PROJ-8982 ¦ Khetan, Umakant ¦ 6072 Lake Linero Drive, Agoura Hills, CA 91301 | Camarillo | Los Angeles County | SCE | Battery;Solar;Back Up Switch | 40884.07 | Permit Submitted | 2026-03-21 | 63 | 2026-05-31 | 133 | 2026-07-28 | 192 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53515443885?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
50613644333 | PROJ-8988 ¦ Desai, Deep ¦ 4609 Cielo Cir, Calabasas, CA 91302 | Camarillo | City of Calabasas | SCE | Solar;Battery;Back Up Switch | 48051.46 | Permit Submitted | 2026-03-22 | 64 | 2026-05-31 | 134 | 2026-07-29 | 193 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/50613644333?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53895055179 | PROJ-8997 ¦ Gurich, Mark P ¦ 1967 Clarkia St, Simi Valley, CA 93065 | Camarillo | Simi Valley | SCE | Battery;Solar;Back Up Switch | 40057.15 | Permit Submitted | 2026-03-24 | 66 | 2026-06-02 | 136 | 2026-07-31 | 195 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53895055179?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search
53021393569 | PROJ-8922 ¦ Horne, Eric ¦ 2981 Sarah Ct, Newbury Park, CA 91320 | Camarillo | Thousand Oaks | SCE | Battery | 18482.4 | Permit Submitted | 2026-04-04 | 77 | 2026-06-30 | 164 | 2026-08-20 | 215 | Scheduled | https://app.hubspot.com/contacts/21710069/record/0-3/53021393569?utm_source=app_16228553_mcp&utm_medium=ai_agent&utm_campaign=search

## Milestone Summary
Milestone | This Month | Next Month | Next 90 Days | Overdue | Total Pipeline
Installation | 8 | 11 | 68 | 60 | 128
Inspection Complete | 10 | 7 | 45 | 38 | 128
Project Complete (PTO) | 6 | 14 | 38 | 26 | 128

## PE Export Format
Project ID | Project Name | Forecasted Install Date | Forecasted Inspection Date | Forecasted PTO Date
18872830551 | PROJ-7075 ¦ Miller, Jason ¦ 2315 S Monroe St, Denver, CO 80210 | 2026-01-14 | 2025-01-16 | 2025-02-19
29502687648 | PROJ-7353 ¦ Frey, Robert ¦ 390 Porter Ranch Rd, Nederland, CO 80466 | 2025-03-04 | 2025-04-13 | 2025-04-26
23041358644 | PROJ-7367 ¦ Chatham, Ken ¦ 1055 Tishlini Lane , Tempelton, CA 93465 | 2025-02-05 | 2025-03-23 | 2025-04-27
28860087969 | PROJ-7370 ¦ Pelisek, Katie ¦ 1620 Geneseo Rd, Paso Robles, CA 93446 | 2025-02-20 | 2025-04-08 | 2025-05-04
33823251811 | PROJ-7729 ¦ Benson, Nancy ¦ 5385 Rancho La Loma Linda Dr, Paso Robles, CA 93446 | 2025-04-22 | 2025-06-07 | 2025-07-12
33719541677 | PROJ-7777 ¦ Slater, Jami ¦ 9700 Sugarloaf Rd, Boulder, CO 80302 | 2025-06-09 | 2025-07-20 | 2025-08-02
28462208159 | PROJ-7292 ¦ Smith, Richard ¦ 34979 Sky Ranch Road, Carmel Valley, CA 93924 | 2025-06-11 | 2025-07-26 | 2025-08-18
35133791026 | PROJ-7932 ¦ Frantz, John ¦ 5001 Lopez Dr, Arroyo Grande, CA 93420 | 2025-06-17 | 2025-08-02 | 2025-09-06
35668319596 | PROJ-8026 ¦ Flores, Robert ¦ 6475 Mira Cielo, San Luis Obispo, CA 93401 | 2025-07-19 | 2025-08-31 | 2025-09-18
33821815854 | PROJ-7731 ¦ Chin, Alan ¦ 12555 Barley Hill Rd, Los Altos Hills, CA 94024 | 2025-05-20 | 2025-07-29 | 2025-09-25
22337108294 | PROJ-8006 ¦ Yan Zhang, Hai ¦ 7 Benchmark Dr, Boulder, CO 80303 | 2025-08-10 | 2025-09-20 | 2025-10-03
38524620936 | PROJ-8162 ¦ Clayton, Dan ¦ 1548 Strand Way, Oceano, CA 93445 | 2025-08-15 | 2025-09-27 | 2025-10-15
38568935058 | PROJ-8194 ¦ Clement, Nick ¦ 708 Sahwatch Street, Colorado Springs, CO 80903 | 2025-09-30 | 2025-10-18 | 2025-10-24
37116101470 | PROJ-7963 ¦ Jerkovich, Nick ¦ 2460 LAUREL AVE, Morro Bay, CA 93442 | 2025-08-13 | 2025-10-18 | 2025-10-31
36741931101 | PROJ-7981 ¦ Aguilar, JaKe ¦ 351 Panay st , Morro Bay, CA 93442 | 2025-08-19 | 2025-10-24 | 2025-11-06
39217639532 | PROJ-8217 ¦ Violetti, Joseph ¦ 2222 Richview Rd, Santa Maria, CA 93455 | 2025-08-24 | 2025-10-13 | 2025-11-26
42444857716 | PROJ-8476 ¦ Dutra, Amanda ¦ 556 Via La Barranca, Arroyo Grande, CA 93420 | 2025-12-05 | 2025-11-06 | 2025-11-28
39611469681 | PROJ-8457 ¦ Gibson, Field ¦ Play Doe Lane, Paso Robles, CA 93446 | 2025-09-30 | 2025-11-12 | 2025-11-30
42860147536 | PROJ-8624 ¦ Stoll, Heather ¦ 1240 Quail Ridge Road, Solvang, CA 93463 | 2025-10-12 | 2025-11-17 | 2025-12-03
40983782672 | PROJ-8381 ¦ Gaalema, Steve ¦ 12930 Morris Trail, Colorado Springs, CO 80908 | 2025-11-10 | 2025-11-28 | 2025-12-03
42265220259 | PROJ-8540 ¦ Norholm, Poul ¦ 301 Fair Oaks Ave, Arroyo Grande, CA 93420 | 2025-12-29 | 2025-11-12 | 2025-12-05
42828630669 | PROJ-8538 ¦ Newman, Korie ¦ 10600 Santa Rita rd, Cayucos, CA 93430 | 2025-10-11 | 2025-11-22 | 2025-12-11
43658515205 | PROJ-8741 ¦ McDonald, Carlotta ¦ 346 Emmons Rd, Cambria, CA 93428 | 2025-11-20 | 2025-12-11 | 2025-12-18
38866623353 | PROJ-8091 ¦ Rakoski, Noah ¦ 20120 Wells Dr, Woodland Hills , CA 91364 | 2025-08-23 | 2025-10-31 | 2025-12-19
12154128687 | PROJ-8618 ¦ Miller, Tamara ¦ 4145 Gray St, Wheat Ridge, CO 80212 | 2025-11-09 | 2025-12-20 | 2026-01-09
39210771611 | PROJ-8170 ¦ Levitt, Sol ¦ 4029 Via Laguna, Santa Barbara, CA 93110 | 2025-09-06 | 2025-11-15 | 2026-01-13
43216836975 | PROJ-8654 ¦ Lingle, Sam ¦ 13825 Overlook Pl, Colorado Springs, CO 80921 | 2026-01-05 | 2026-01-14 | 2026-01-19
45105028218 | PROJ-8740 ¦ Guiltinan, Jeff ¦ 1305 Newport Ave, Arroyo Grande, CA 93420 | 2025-11-11 | 2026-01-01 | 2026-01-23
48169229828 | PROJ-8800 ¦ Ditmanson, Mark ¦ 1277 Castro Rd., Monterey, CA 93940 | 2025-12-09 | 2026-01-14 | 2026-01-29
45151434504 | PROJ-8723 ¦ Baker, Bradley ¦ 12460 Woodruff Dr, Colorado Springs, CO 80921 | 2026-01-05 | 2026-01-23 | 2026-01-29
43487863931 | PROJ-8650 ¦ Rosell, Sean ¦ 933 Xenon Ct, Golden, CO 80401 | 2025-12-04 | 2026-01-06 | 2026-01-29
43125493794 | PROJ-8642 ¦ Hart, Roger Terence ¦ 1234 Doris Cir, Erie, CO 80516 | 2025-12-12 | 2026-01-17 | 2026-01-29
43562208539 | PROJ-8634 ¦ Bryan, Jake ¦ 4691 Tepusquet Rd, Santa Maria, CA 93454 | 2025-10-29 | 2025-12-19 | 2026-02-01
48277044338 | PROJ-8811 ¦ Hall, Wayne ¦ 3255 Ryan Rd, Creston, CA 93432 | 2025-12-13 | 2026-01-18 | 2026-02-03
43067096885 | PROJ-8743 ¦ Gantman, Marissa ¦ 2309 Watersong Cir, Longmont, CO 80504 | 2025-12-28 | 2026-01-31 | 2026-02-03
48893857114 | PROJ-8830 ¦ Wagner, Kelsey ¦ 315 S Mason St, Arroyo Grande, CA 93420 | 2025-12-17 | 2026-01-21 | 2026-02-06
43784573251 | PROJ-8694 ¦ Morales, Michelle ¦ 11542 W Lake Dr, Littleton, CO 80127 | 2025-12-13 | 2026-01-15 | 2026-02-07
40892008480 | PROJ-8660 ¦ Seidle, Nathan ¦ 2779 River Drive, Alma, CO 80420 | 2025-12-09 | 2026-01-13 | 2026-02-08
49472329890 | PROJ-8843 ¦ Londono, Juan ¦ 753 Guy Turner, Camarillo, CA 93010 | 2025-12-21 | 2026-01-26 | 2026-02-11
41519729833 | PROJ-8677 ¦ SHAY, BENJAMIN ¦ 134 S Pontiac St, Denver, CO 80230 | 2025-12-17 | 2026-01-08 | 2026-02-11
43711803674 | PROJ-8686 ¦ Maddox, Glenn ¦ 9083 Sheridan Loop, Salida, CO 81201 | 2025-12-15 | 2026-01-19 | 2026-02-14
28809813653 | PROJ-8762 ¦ Ellis, David ¦ 11295 Los Osos Valley Rd #27, San Luis Obispo, CA 93405 | 2025-12-05 | 2026-01-12 | 2026-02-16
44027054617 | PROJ-8752 ¦ Davis, Glynn ¦ 5665 Encima Ct, Atascadero, CA 93422 | 2025-12-26 | 2026-01-30 | 2026-02-22
42027887227 | PROJ-8450 ¦ Khalilzadeh, Afshin ¦ 25335 Prado De Los Gansos, Calabasas, CA 91302 | 2025-10-20 | 2025-12-29 | 2026-02-26
48425963637 | PROJ-8812 ¦ Ammon, Thomas ¦ 1722 BEE CANYON RD, Arroyo Grande, CA 93420 | 2026-01-15 | 2026-02-08 | 2026-02-27
46572128347 | PROJ-8781 ¦ Pierce, Carol ¦ 1761 Paradise Meadows Lane , Templeton, CA 93465 | 2025-12-08 | 2026-01-23 | 2026-02-27
46048497773 | PROJ-8778 ¦ Rees, Christiaan ¦ 18470 Academy Cir, Monument, CO 80132 | 2026-02-06 | 2026-02-24 | 2026-03-01
41564768293 | PROJ-8472 ¦ Heiting, Craig ¦ 32000 Watergate Court, Westlake Village, CA 91361 | 2025-12-15 | 2026-01-03 | 2026-03-03
46256518952 | PROJ-8754 ¦ Kyu Park, Byung ¦ 4237 Lantana Ct, Santa Maria, CA 93455 | 2025-12-02 | 2026-01-22 | 2026-03-07
48488136580 | PROJ-8823 ¦ Thompson, Cliff ¦ 358 N Court St, Baywood-Los Osos, CA 93402 | 2025-12-12 | 2026-02-08 | 2026-03-15
42755755408 | PROJ-8609 ¦ Case, Jared ¦ 367 Nueve Ct, Camarillo, CA 93012 | 2025-11-12 | 2026-01-21 | 2026-03-21
48512075589 | PROJ-8880 ¦ Bethel, Barbara ¦ 1111 Long View , Pismo Beach, CA 93449 | 2026-01-26 | 2026-03-02 | 2026-03-26
53131630629 | PROJ-8930 ¦ Kuhlmann, Kurt ¦ 295 Via Piedras Blancas, san simeon, CA 93452 | 2026-02-07 | 2026-03-15 | 2026-03-31
43878057266 | PROJ-8656 ¦ L Tansey, Kevin ¦ 2771 Acacia St, Camarillo, CA 93012 | 2025-11-24 | 2026-02-02 | 2026-04-02
52345682436 | Wendel, Doug ¦ 4181 Niblick Dr, Longmont, CO 80503 | 2026-02-11 | 2026-03-18 | 2026-04-03
45716506670 | PROJ-8851 ¦ Atkinson, Pamela Meyla ¦ 5260 Chauplin Ave, Atascadero, CA 93422 | 2026-02-04 | 2026-03-11 | 2026-04-03
51930719144 | PROJ-8883 ¦ Nenow, Andrea ¦ 393 Eric Lane, Templeton, CA 93465 | 2026-02-02 | 2026-03-16 | 2026-04-04
52342352176 | PROJ-8976 ¦ Macchi, C.R. ¦ 17085 W 62nd Cir, Golden, CO 80403 | 2026-02-14 | 2026-03-22 | 2026-04-07
42969550992 | PROJ-8632 ¦ Johnston, Jeanette ¦ Santa Fe 2nd NW of Ocean Ave, Carmel, CA 93921 | 2025-12-21 | 2026-03-15 | 2026-04-07
43817717324 | PROJ-8683 ¦ Richards, Amy M ¦ 645 Skyline Rd, Ventura, CA 93003 | 2025-11-30 | 2026-02-08 | 2026-04-08
53999169648 | PROJ-8999 ¦ Lyons, Ella ¦ 1710 Utah St, Golden, CO 80401 | 2026-02-17 | 2026-03-25 | 2026-04-09
53561556257 | PROJ-9005 ¦ Cruz Jr, Alcidez ¦ 17910 slavin way, Platteville, CO 80651 | 2026-02-18 | 2026-03-25 | 2026-04-10
39669410607 | PROJ-8641 ¦ Liu, Wei ¦ 25380 Quail Summit Lane, Monterey, CA 93940 | 2025-12-24 | 2026-03-18 | 2026-04-10
43946261506 | PROJ-8697 ¦ Castillo, David ¦ 1878 Hobart Drive, Camarillo, CA 93010 | 2025-12-03 | 2026-02-11 | 2026-04-11
52610867858 | PROJ-8910 ¦ Tullius, Jami ¦ 5220 Topaz Dr, Colorado Springs, CO 80918 | 2026-03-27 | 2026-04-14 | 2026-04-20
52479200092 | PROJ-8909 ¦ Sekelsky, Kristin ¦ 6552 Courtland Place, Colorado Springs, CO 80924 | 2026-03-29 | 2026-04-16 | 2026-04-22
52037859506 | PROJ-8884 ¦ Davis, John ¦ 631 Huajatolla Valley Estates Dr, La Veta, CO 81055 | 2026-03-20 | 2026-04-17 | 2026-04-23
45369375558 | PROJ-8730 ¦ Diep, Jason ¦ 2277 El Nido Ct, Camarillo, CA 93010 | 2025-12-16 | 2026-02-24 | 2026-04-24
51931621262 | PROJ-8904 ¦ Sobrevilla, Saidel ¦ 8661 Hunters Hill Ln , Littleton, CO 80125 | 2026-03-09 | 2026-04-10 | 2026-04-26
51956310800 | PROJ-8903 ¦ Martinez, Ricardo ¦ 8727 Hunters Hill Ln, Littleton, CO 80125 | 2026-03-09 | 2026-04-10 | 2026-04-26
45934137926 | PROJ-8749 ¦ Casselman, David ¦ 27002 Malibu Cove Colony Dr, Malibu, CA 90265 | 2025-12-22 | 2026-03-03 | 2026-04-30
52390853461 | PROJ-8911 ¦ Varghese, Julian ¦ 7420 Mount Meeker Road, Longmont, CO 80503 | 2026-03-14 | 2026-04-23 | 2026-05-07
46447596822 | PROJ-8767 ¦ Smallwood, Brian ¦ 2809 Acacia St, Camarillo, CA 93012 | 2025-12-29 | 2026-03-09 | 2026-05-07
53630691648 | PROJ-8974 ¦ Wehner, Chad ¦ 4630 Topaz Dr, Colorado Springs, CO 80918 | 2026-04-08 | 2026-05-10 | 2026-05-08
50895749181 | Pyziak, David M ¦ 4229 Captain Jack Ln, Colorado Springs, CO 80924 | 2026-04-14 | 2026-05-02 | 2026-05-08
52384418094 | PROJ-8905 ¦ Pearson, LESLIE ¦ 5352 Devils Head Cir, Golden, CO 80403 | 2026-03-18 | 2026-04-20 | 2026-05-13
52071909996 | PROJ-8915 ¦ Sjostrom, Bradley ¦ 22568 Westview Ave, Golden, CO 80401 | 2026-03-19 | 2026-04-21 | 2026-05-14
53412268712 | PROJ-8952 ¦ Blondeau, Donna ¦ 8780 Skyland Dr, Longmont, CO 80503 | 2026-03-24 | 2026-05-03 | 2026-05-16
52883875648 | PROJ-8907 ¦ Fitch, Aide ¦ 993 Arapahoe Cir, Louisville, CO 80027 | 2026-03-21 | 2026-04-21 | 2026-05-16
11761029909 | PROJ-8955 ¦ Lu, Cheng-Hsuan ¦ 4569 S Meadow Dr, Boulder, CO 80301 | 2026-03-24 | 2026-05-03 | 2026-05-17
52833472822 | PROJ-8914 ¦ Coombs, Michael ¦ 5734 Pinon Dr, Elizabeth, CO 80107 | 2026-03-30 | 2026-05-06 | 2026-05-19
52244751445 | PROJ-8908 ¦ Martin, Edward ¦ 155 Southmoor Dr, Denver, CO 80220 | 2026-03-25 | 2026-04-16 | 2026-05-20
47325983380 | PROJ-8797 ¦ Feeney, Patrick ¦ 4641 Pepper Mill St, Moorpark, CA 93021 | 2026-01-12 | 2026-03-23 | 2026-05-21
49708527886 | PROJ-8937 ¦ Pratsch, Eric ¦ 15483 W 51st Pl, Golden, CO 80403 | 2026-03-27 | 2026-04-29 | 2026-05-22
48830868904 | PROJ-8838 ¦ Simpkins, James ¦ 23129 Erwin St, Woodland Hills, CA 91367 | 2026-01-25 | 2026-04-04 | 2026-05-23
20720050747 | PROJ-8947 ¦ Hellner, Richard ¦ 19770 W 57th Lane, Golden, CO 80403 | 2026-03-28 | 2026-05-01 | 2026-05-23
42826488415 | PROJ-8929 ¦ Landrum, Adam ¦ 358 Mulberry Cir, Broomfield, CO 80020 | 2026-03-10 | 2026-05-01 | 2026-05-25
52607086402 | PROJ-8928 ¦ Schraad, Daryl ¦ 425 sawmill creek road, Evergreen, CO 80439 | 2026-04-07 | 2026-05-14 | 2026-05-26
48475133869 | PROJ-8810 ¦ Rahane, Annasaheb ¦ 194 Rose St, Fillmore, CA 93015 | 2026-01-17 | 2026-03-28 | 2026-05-26
43910946823 | PROJ-8785 ¦ Hobbs, Jeff ¦ 13762 Center St, Carmel Valley, CA 93924 | 2026-02-08 | 2026-05-03 | 2026-05-26
53501152385 | PROJ-8979 ¦ Koken, Daniel ¦ 1357 Gold Mine Ln, Evergreen, CO 80439 | 2026-04-01 | 2026-05-04 | 2026-05-27
53131685682 | PROJ-8966 ¦ HAYCRAFT, JEANNIE ¦ 16691 w 55th pl, golden, CO 80403 | 2026-04-01 | 2026-05-04 | 2026-05-27
52865379253 | Packer, Bill ¦ 951 Sunflower Street, Louisville, CO, USA, Louisville, CO 80027 | 2026-03-31 | 2026-05-01 | 2026-05-27
48886868240 | PROJ-8819 ¦ Narang, Mukesh ¦ 489 Marymount Ct , Ventura , CA 93003 | 2026-01-18 | 2026-03-29 | 2026-05-27
48816887137 | PROJ-8818 ¦ Falkenhagen, Scott ¦ 23565 Park Belmonte, Calabasas, CA 91302-1702 | 2026-01-18 | 2026-03-29 | 2026-05-27
48171013491 | PROJ-8815 ¦ Sorensen, Paul ¦ 4220 Mariposa Dr , Santa Barbara, CA 93110 | 2026-01-18 | 2026-03-29 | 2026-05-27
29775766932 | PROJ-8975 ¦ Gawrych, Liliya ¦ 6996 Skunk Alley, Evergreen, CO 80439 | 2026-04-01 | 2026-05-04 | 2026-05-27
17694760719 | Himmel, Evan ¦ 17769 W 95th Pl, Arvada, CO 80007 | 2026-04-01 | 2026-05-05 | 2026-05-27
53290804084 | PROJ-8925 ¦ Bailey, Christine ¦ 2002 W 32nd St, Pueblo, CO 81008 | 2026-03-19 | 2026-04-24 | 2026-05-29
53278160475 | PROJ-8924 ¦ McNeil, Jessie ¦ 4029 Hillside Dr, Pueblo, CO 81008 | 2026-03-19 | 2026-04-24 | 2026-05-29
52836777632 | PROJ-8987 ¦ SKIGEN, SARAH ¦ 14905 W 54th Ave, Golden, CO 80403 | 2026-04-03 | 2026-05-06 | 2026-05-29
48946535507 | PROJ-8824 ¦ Hillard, Mary Sue ¦ 1891 Lakehurst Avenue, Camarillo, CA 93010-3827 | 2026-01-20 | 2026-03-31 | 2026-05-29
11759540266 | PROJ-8935 ¦ Rooney, Chelsea ¦ 80 Defrance Way, Golden, CO 80401 | 2026-03-29 | 2026-05-03 | 2026-05-29
51728745368 | PROJ-8946 ¦ Plunkett, Cris ¦ 517 Venus Ave., Lompoc, CA 93436 | 2026-02-25 | 2026-04-16 | 2026-05-30
49134683809 | PROJ-8832 ¦ Harris, Robert ¦ 669 Larchmont St , Simi Valley , CA 93065 | 2026-01-21 | 2026-04-01 | 2026-05-30
46676373629 | PROJ-8945 ¦ Whittemore, Todd ¦ 35471 Hidden Mesa Drive, Pueblo, CO 81006 | 2026-03-29 | 2026-04-28 | 2026-06-01
49152858025 | PROJ-8840 ¦ Jasechko, Scott ¦ 7097 scripps crescent, goleta, CA 93117 | 2026-01-25 | 2026-04-05 | 2026-06-03
51953666487 | PROJ-8972 ¦ Xu, Sarah ¦ 3289 S Eudora St, Denver, CO 80222 | 2026-04-09 | 2026-05-01 | 2026-06-04
53782899356 | Nuccio, Vito ¦ 15506 W Vassar Ave, Denver, CO 80228 | 2026-04-02 | 2026-05-11 | 2026-06-05
52918916683 | Gangadhar, Akshata ¦ 724 Via Arroyo, Ventura , CA 93003 | 2026-04-02 | 2026-05-11 | 2026-06-05
52316057972 | Schlander, Mark ¦ 330 Oakwood Pl, Boulder, CO 80304 | 2026-04-02 | 2026-05-11 | 2026-06-05
51437855035 | Pratsch, Eric ¦ 15483 W 51st Pl, Golden, CO 80403 | 2026-04-02 | 2026-05-11 | 2026-06-05
28708917322 | Hansen, Gregory ¦ 3235 10th Street, Boulder, CO 80304 | 2026-04-02 | 2026-05-11 | 2026-06-05
52228146290 | PROJ-8994 ¦ Martin, Philip ¦ 6318 Oakwood Ct, Loveland, CO 80538 | 2026-04-07 | 2026-05-11 | 2026-06-06
52106295185 | PROJ-8993 ¦ Vanatt, Trulane ¦ 15298 W Baker Ave, Lakewood, CO 80228 | 2026-04-09 | 2026-05-20 | 2026-06-10
15941713193 | PROJ-8934 ¦ Beckett, William ¦ 13117 W 73rd Lane , Arvada, CO 80005 | 2026-04-05 | 2026-05-20 | 2026-06-10
53527775873 | PROJ-8995 ¦ Trifon, Lisa ¦ 3715 Longwood Ave, Boulder, CO 80305 | 2026-04-16 | 2026-05-27 | 2026-06-11
51527015294 | PROJ-8942 ¦ Zito, Heather ¦ 16594 W 93rd Way, Arvada, CO 80007 | 2026-04-07 | 2026-05-22 | 2026-06-12
47284182065 | PROJ-8957 ¦ Reinicke, Nick ¦ 7180 Van Gordon Street, Arvada, CO 80004 | 2026-04-07 | 2026-05-22 | 2026-06-12
53548594469 | PROJ-8978 ¦ Anderson, Jason ¦ 12916 W 61st Cir, Arvada, CO 80004 | 2026-04-11 | 2026-05-26 | 2026-06-16
51269373207 | PROJ-8869 ¦ Temesvary, Frank ¦ 31579 Sea Level Drive, Malibu, CA 90265 | 2026-02-16 | 2026-04-27 | 2026-06-25
52230534414 | PROJ-8898 ¦ Psaros, Paris ¦ 7758 Jenna Dr, Goleta, CA 93117 | 2026-03-01 | 2026-05-10 | 2026-07-08
52678381440 | PROJ-8919 ¦ Smith, Adrian ¦ 106 Golden Glen Drive, Simi Valley, CA 93065 | 2026-03-09 | 2026-05-18 | 2026-07-16
51999614547 | Landis, Vance ¦ 46304 Pfeiffer Ridge Road, Big Sur, CA 93920 | 2026-04-02 | 2026-06-25 | 2026-07-18
53515443885 | PROJ-8982 ¦ Khetan, Umakant ¦ 6072 Lake Linero Drive, Agoura Hills, CA 91301 | 2026-03-21 | 2026-05-31 | 2026-07-28
50613644333 | PROJ-8988 ¦ Desai, Deep ¦ 4609 Cielo Cir, Calabasas, CA 91302 | 2026-03-22 | 2026-05-31 | 2026-07-29
53895055179 | PROJ-8997 ¦ Gurich, Mark P ¦ 1967 Clarkia St, Simi Valley, CA 93065 | 2026-03-24 | 2026-06-02 | 2026-07-31
53021393569 | PROJ-8922 ¦ Horne, Eric ¦ 2981 Sarah Ct, Newbury Park, CA 91320 | 2026-04-04 | 2026-06-30 | 2026-08-20