## Executive Summary
PHOTON BROTHERS - WEEKLY OPERATIONS REPORT
Week of January 12, 2026
KEY METRICS
Total Active Projects | 478
Ready to Build | 26
Participate Energy Projects | 107
Total Pipeline Value | $20.34M
PE Compliance Rate | 80.4%
CRITICAL ALERTS
[HIGH] Inspection Backlog | 121 projects stuck in Inspection stage | $4766k pipeline value affected
[HIGH] Participate Energy Milestone Risk | 38 PE projects approaching milestone deadlines | $1517k in PE revenue at risk
THIS WEEK'S PRIORITIES
19 installs due this week | $499k value
11 inspections due this week | Coordinate with inspectors
32 PE projects with overdue milestones | URGENT - affects PE compliance

## By Location
Location | Total | RTB | Overdue Install | This Week | PE Projects | Pipeline Value
Westminster | 149 | 4 | 113 | 5 | 17 | 7110567.04
San Luis Obispo | 121 | 9 | 115 | 2 | 29 | 4767138.82
Centennial | 106 | 1 | 67 | 6 | 23 | 4989703.07
Camarillo | 64 | 10 | 51 | 5 | 25 | 1971149.41
Colorado Springs | 34 | 1 | 20 | 1 | 13 | 1454927.76

## This Week Schedule
Priority | Project | Location | Stage | Install Date | Value | PE | Notes
1 | PROJ-7370 | San Luis Obispo | Ready To Build | 2026-01-18 | 32950 | Yes | CRITICAL: 333 days overdue
2 | PROJ-7292 | San Luis Obispo | Ready To Build | 2026-01-18 | 21070 | Yes | CRITICAL: 221 days overdue
3 | PROJ-7945 | San Luis Obispo | Ready To Build | 2026-01-18 | 28399.55 |  | CRITICAL: 200 days overdue
4 | PROJ-8006 | Westminster | Ready To Build | 2026-01-18 | 32006.72 | Yes | CRITICAL: 161 days overdue
5 | PROJ-8091 | Camarillo | Ready To Build | 2026-01-18 | 63744.75 | Yes | CRITICAL: 149 days overdue
6 | PROJ-7981 | San Luis Obispo | Ready To Build | 2026-01-18 | 12043.47 | Yes | CRITICAL: 152 days overdue
7 | PROJ-8182 | Westminster | Ready To Build | 2026-01-18 | 37387.86 |  | CRITICAL: 127 days overdue
8 | PROJ-8128 | Westminster | Ready To Build | 2026-01-18 | 49459.9 |  | CRITICAL: 117 days overdue
9 | PROJ-8609 | Camarillo | Ready To Build | 2026-01-18 | 29944.34 | Yes | CRITICAL: 68 days overdue
10 | PROJ-8596 | San Luis Obispo | Ready To Build | 2026-01-18 | 36274 |  | CRITICAL: 92 days overdue
11 | PROJ-8466 | Camarillo | Ready To Build | 2026-01-18 | 5600 |  | CRITICAL: 89 days overdue
12 | PROJ-8683 | Camarillo | Ready To Build | 2026-01-18 | 55767.89 | Yes | CRITICAL: 49 days overdue
13 | PROJ-8697 | Camarillo | Ready To Build | 2026-01-18 | 18203.94 | Yes | CRITICAL: 47 days overdue
14 | PROJ-8762 | San Luis Obispo | Ready To Build | 2026-01-18 | 25971.4 | Yes | CRITICAL: 44 days overdue
15 | PROJ-8535 | Centennial | Ready To Build | 2026-01-18 | 18291 |  | CRITICAL: 61 days overdue
16 | PROJ-8540 | San Luis Obispo | Ready To Build | 2026-01-18 | 42771.6 | Yes | Overdue: 20 days
17 | PROJ-8730 | Camarillo | Ready To Build | 2026-01-18 | 42966 | Yes | CRITICAL: 34 days overdue
18 | PROJ-8632 | San Luis Obispo | Ready To Build | 2026-01-18 | 24219 | Yes | Overdue: 28 days
19 | PROJ-8749 | Camarillo | Ready To Build | 2026-01-18 | 29431.08 | Yes | Overdue: 27 days
20 | PROJ-8723 | Colorado Springs | Ready To Build | 2026-01-18 | 33489.9 | Yes | Overdue: 13 days
21 | PROJ-8810 | Camarillo | Ready To Build | 2026-01-18 | 18203.94 | Yes | Overdue: 1 days
22 | PROJ-8846 | San Luis Obispo | Ready To Build | 2026-01-18 | 23800 |  | Overdue: 5 days
23 | PROJ-8832 | Camarillo | Ready To Build | 2026-01-18 | 13198.8 | Yes | Due in 3 days
24 | PROJ-8771 | Westminster | Ready To Build | 2026-01-18 | 34258 |  | Due in 2 days
25 | PROJ-9004 | Unknown | Ready To Build |  | 41702.08 |  | Due in 73 days

## PE Milestones
Project | Location | Inspection Date | Insp Status | PTO Date | PTO Status | Value
PROJ-7075 | Centennial | 2025-01-16 | OVERDUE | 2025-02-19 | OVERDUE | 72563.2
PROJ-7367 | San Luis Obispo | 2025-03-22 | OVERDUE | 2025-04-26 | OVERDUE | 12334
PROJ-7370 | San Luis Obispo | 2025-04-08 | OVERDUE | 2025-05-03 | OVERDUE | 32950
PROJ-7353 | Westminster | 2025-04-12 | OVERDUE | 2025-04-26 | OVERDUE | 30872.4
PROJ-7729 | San Luis Obispo | 2025-06-06 | OVERDUE | 2025-07-11 | OVERDUE | 43621.6
PROJ-7777 | Westminster | 2025-07-19 | OVERDUE | 2025-08-02 | OVERDUE | 37194.8
PROJ-7292 | San Luis Obispo | 2025-07-26 | OVERDUE | 2025-08-18 | OVERDUE | 21070
PROJ-7932 | San Luis Obispo | 2025-08-01 | OVERDUE | 2025-09-05 | OVERDUE | 41702.08
PROJ-8026 | San Luis Obispo | 2025-08-31 | OVERDUE | 2025-09-18 | OVERDUE | 55000
PROJ-8006 | Westminster | 2025-09-19 | OVERDUE | 2025-10-03 | OVERDUE | 32006.72
PROJ-8162 | San Luis Obispo | 2025-09-26 | OVERDUE | 2025-10-14 | OVERDUE | 37146.9
PROJ-8217 | San Luis Obispo | 2025-10-13 | OVERDUE | 2025-11-26 | OVERDUE | 52018.72
PROJ-7963 | San Luis Obispo | 2025-10-17 | OVERDUE | 2025-10-30 | OVERDUE | 38994.34
PROJ-8194 | Colorado Springs | 2025-10-18 | OVERDUE | 2025-10-24 | OVERDUE | 33837.15
PROJ-7981 | San Luis Obispo | 2025-10-24 | OVERDUE | 2025-11-06 | OVERDUE | 12043.47
PROJ-8091 | Camarillo | 2025-10-30 | OVERDUE | 2025-12-18 | OVERDUE | 63744.75
PROJ-8476 | San Luis Obispo | 2025-11-05 | OVERDUE | 2025-11-28 | OVERDUE | 55264
PROJ-8457 | San Luis Obispo | 2025-11-11 | OVERDUE | 2025-11-29 | OVERDUE | 49041.58
PROJ-8540 | San Luis Obispo | 2025-11-12 | OVERDUE | 2025-12-05 | OVERDUE | 42771.6
PROJ-8381 | Colorado Springs | 2025-11-28 | OVERDUE | 2025-12-03 | OVERDUE | 27402.53
PROJ-8634 | San Luis Obispo | 2025-12-18 | OVERDUE | 2026-01-31 | URGENT | 37679.56
PROJ-8618 | Centennial | 2025-12-19 | OVERDUE | 2026-01-08 | OVERDUE | 33839.37
PROJ-8450 | Camarillo | 2025-12-28 | OVERDUE | 2026-02-25 | UPCOMING | 94561.91
PROJ-8740 | San Luis Obispo | 2025-12-31 | OVERDUE | 2026-01-23 | URGENT | 37403.08
PROJ-8472 | Camarillo | 2026-01-02 | OVERDUE | 2026-03-02 | UPCOMING | 30478
PROJ-8650 | Centennial | 2026-01-06 | OVERDUE | 2026-01-28 | URGENT | 56203.17
PROJ-8677 | Centennial | 2026-01-08 | OVERDUE | 2026-02-11 | UPCOMING | 41314.62
PROJ-8762 | San Luis Obispo | 2026-01-11 | OVERDUE | 2026-02-16 | UPCOMING | 25971.4
PROJ-8660 | Colorado Springs | 2026-01-12 | OVERDUE | 2026-02-07 | URGENT | 30059.08
PROJ-8654 | Colorado Springs | 2026-01-14 | OVERDUE | 2026-01-19 | URGENT | 28728
PROJ-8694 | Centennial | 2026-01-15 | OVERDUE | 2026-02-06 | URGENT | 30825.06
PROJ-8642 | Westminster | 2026-01-16 | OVERDUE | 2026-01-28 | URGENT | 63792.64
PROJ-8686 | Colorado Springs | 2026-01-18 | URGENT | 2026-02-13 | UPCOMING | 42314.62
PROJ-8609 | Camarillo | 2026-01-20 | URGENT | 2026-03-20 | ON TRACK | 29944.34
PROJ-8754 | San Luis Obispo | 2026-01-21 | URGENT | 2026-03-06 | ON TRACK | 52822.88
PROJ-8723 | Colorado Springs | 2026-01-23 | URGENT | 2026-01-29 | URGENT | 33489.9
PROJ-8752 | San Luis Obispo | 2026-01-30 | URGENT | 2026-02-21 | UPCOMING | 39461.18
PROJ-8743 | Westminster | 2026-01-31 | URGENT | 2026-02-03 | URGENT | 16743.65
PROJ-8656 | Camarillo | 2026-02-01 | URGENT | 2026-04-01 | ON TRACK | 62941.49
PROJ-8823 | San Luis Obispo | 2026-02-07 | UPCOMING | 2026-03-14 | ON TRACK | 20109.6
PROJ-8812 | San Luis Obispo | 2026-02-08 | UPCOMING | 2026-02-26 | UPCOMING | 32124
PROJ-8683 | Camarillo | 2026-02-08 | UPCOMING | 2026-04-08 | ON TRACK | 55767.89
PROJ-8697 | Camarillo | 2026-02-10 | UPCOMING | 2026-04-10 | ON TRACK | 18203.94
PROJ-8800 | San Luis Obispo | 2026-02-17 | UPCOMING | 2026-03-14 | ON TRACK | 74252.67
PROJ-8811 | San Luis Obispo | 2026-02-21 | ON TRACK | 2026-03-18 | ON TRACK | 36566.11
PROJ-8730 | Camarillo | 2026-02-23 | ON TRACK | 2026-04-23 | ON TRACK | 42966
PROJ-8778 | Colorado Springs | 2026-02-24 | ON TRACK | 2026-03-01 | UPCOMING | 26837.91
PROJ-8880 | San Luis Obispo | 2026-03-01 | ON TRACK | 2026-03-26 | ON TRACK | 10469.34
PROJ-8749 | Camarillo | 2026-03-02 | ON TRACK | 2026-04-30 | ON TRACK | 29431.08
PROJ-8851 | San Luis Obispo | 2026-03-11 | ON TRACK | 2026-04-02 | ON TRACK | 53309.36

## Bottleneck Analysis
BOTTLENECK ANALYSIS REPORT
Generated: 2026-01-17 03:48
Inspection Backlog | HIGH
Description: | 121 projects stuck in Inspection stage
Impact: | $4766k pipeline value affected
Recommendation: | Review Inspection process - consider adding resources or expediting
Participate Energy Milestone Risk | HIGH
Description: | 38 PE projects approaching milestone deadlines
Impact: | $1517k in PE revenue at risk
Recommendation: | Prioritize PE projects in scheduling queue
LOCATION EFFICIENCY SCORES
Location | Avg Cycle Days | Overdue % | Score
Westminster | 171.3 | 75.8% | -61.5
Centennial | 144.1 | 63.2% | -35.3
Colorado Springs | 137.1 | 58.8% | -27.4
San Luis Obispo | 340.7 | 95.0% | -165.4
Camarillo | 145.9 | 79.7% | -52.6